## Supplier Governance
Please complete the box below prior to submission
To Be Completed by Supplier
Completed By:
Organisation:
Assessment Date:
To Be Completed by NHS Digital*
Reviewed by:
Stakeholder Group:
Review Date:
Comments:
* NHS Digital to create further box(es) as necessary for stakeholder review.
Copyright © 2020 Health and Social Care Information Centre.
NHS Digital is the trading name of the Health and Social Care Information Centre.

## RAW Governance (NHS-D) (hidden)
Risk Assessment Workshop Governance
Document Purpose
This tab is to be completed if the risks have been identified as part of an NHS Digital Risk Assessment Workshop (RAW)
Risk Assessment Workshop Governance
| Workshop Title: | Signing Service API Connecting Systems Risk Log Workshop
| Workshop Lead: | Simon Branton
| Workshop Attendees | Tim Coates | Senior Technical Architect
|  | Sam Evans | Business Analyst, EPS
|  | Dan Jones | Developer, EPS
|  | Alex McCormick | Senior Developer, EPS
|  | Tahmina Rokib | Clinical Lead
|  | Nishali Patel | Clinical Lead
|  | Jen Redman | Lead Product Manager, EPS
| Workshop Date(s): | 2022-09-27
Approved By:
| Post Workshop Amendments: | Name | Date | Reason for Update | Approved By
Status:
Do not send DRAFT risk log to external suppliers.
Copyright © 2020 Health and Social Care Information Centre.
NHS Digital is the trading name of the Health and Social Care Information Centre.

## Log Template Version History (hidden)
Amendment History
Version | Date | Amendment History
0.26 | 2020-06-12 | Updates following extensive discussions with ADLs and Matt Barrow.
0.27 | 2020-06-12 | Updates following review by Simon Lee
1 | 2020-06-15 | Issued for use.
1.1 | 2020-06-17 | RAW Governance tab updated to avoid issues with TASER upload (< and > removed)
1.2 | 2020-06-23 | Filtering corrected.
1.3 | 2020-06-24 | Formulas for programme Risk Threshold added and Guidance updated. Pick List for Risk Grouping added. Guidance tab moved next to Risk Log tab.
1.4 | 2020-06-29 | Cosmetic changes for ease of use. Updates to Guidance tab.
2 | 2020-07-01 | Up issued as default version.
2.1 | 2020-10-09 | SL - Removed some rogue numbers in Impact Scales tab
2.2 | 2020-11-04 | SL - Amended the formula in Risk Log tab for column O to bring all clinical risks into scope for assurance regardless of QMM threshold score. Also added reference to Cyber as an assurance group in the guidance tab.
2.3 | 2020-11-12 | SL - Reinstated Cyber Security impact scales to log.
2.4 | 2020-11-19 | SL - Amended the formula for Column O to include the state of column K.
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Paul Butterworth |  | Head of Assurance
Phil Morton |  | Head of Assurance
Emma Bell |  | Test & Assurance Lead | 2020-06-19 | 1
Richard Dobson |  | Assurance Manager | 2020-06-20 | 1
Alan Laithwaite |  | Assurance Manager | 2020-06-19 | 1
Matthew Barrow |  | Consultant
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Paul Butterworth |  | Head of Assurance
Phil Morton |  | Head of Assurance
Distribution
NHS Digital
Document Status:
ISSUED

## Pick Lists (hidden)
Primary Impact Area | QMM Threshold | Impact Rating | Likelihood Rating (Cols G and L) | In Scope for Assurance ? | Assurance Group | High Level Assurance Mitigation | Risk Log Status | Is the mitigation in place? | Programme Risk Threshold | Phase | Risk Grouping
Clinical | 0 | 1 | 1 | Y | SA | Collaborative Engagement | DRAFT | Y | 1 | alpha | Communication
Cyber Security | 1 | 2 | 2 | N | Programme | Embedded Assurance | Approved | N | 2 | beta | Contractual
Data Quality | 8 | 3 | 3 |  | CSG | Review Submitted Evidence |  |  | 3 | Pilot | Data - read
IG | 15 | 4 | 4 |  | Service Management | Review Spine Log Files |  |  | 4 | Live | Data - write
Interoperability |  | 5 | 5 |  | Cyber Security | Review Test Coverage |  |  | 5 | National Roll-out | Functional
National Datasets |  |  | N/A |  | Other (Specify in Elaboration Column) | Tailored Witness Test |  |  | 6 | Phase 1 | Interface
National Services | [5 empty] | Other (Specify in Elaboration Column) |  |  | 7 | Phase 2 | Missing requirement
System/Solution Integrity | [8 empty] | 8 | Phase 3 | Non-functional
Usability | [8 empty] | 9 | Phase 4 | Software error
[9 empty] | 10 | n/a | User journey
11
12
13
14
15
0

## Guidance
Purpose
This is the Risk Log template, used by NHS Digital Solution Assurance to analyse system and/or service risks. Further interaction between the Supplier and NHS Digital will implement controls to ensure that mitigations are deployed correctly. The context in which this template is to be used is provided by the RAW Service Definition.
IMPORTANT: This Risk Log does not replace the Clinical Hazard Log, and where clinical risks are identified, they should be added to the relevant clinical hazard log.
Note on use of formula within this spreadsheet: They are indicated with Calculated in heading on the Risk Log tab, these fields automatically calculate their values via defined formula. If these are not updating as per your selections then please check your Calculation settings in Excel, Please ensure you DO NOT DELETE the formula, if you do then please re-insert by dragging down from formula from the cell above.
Guidance on how to complete the spreadsheet
Activity | Instructions
NHS Digital internal risk workshop | Complete the RAW Governance tab first. Complete columns A to G of the Risk Log tab as per guidance below. It may also be possible to complete cell values for columns G and H for some rows if you are able to identify likelihood without supplier input.
A Supplier responding to a set of risks supplied by NHS Digital | Complete the Supplier Governance tab. Complete columns H to M of the Risk Log tab as per guidance below.
NHS Digital reviewing and completing the assurance sections within the spreadsheet | Complete columns N to R of the Risk Log tab as per guidance below.
A supplier using the Risk Log template to create their own set of risks | Complete columns A to M of the Risk Log tab as per guidance below.
A Supplier is: Any organisation or group whom are responsible for the delivery of Healthcare software into the NHS (within England). They could be internal or external to the NHS.
General Guidance on Governance
Suppliers are required to complete their section of the Supplier Governance tab when using the Risk Log. NHS Digital are required to complete their section(s) of Supplier Governance following review of the supplier submission.
Use of RAW Governance TAB is reserved for use by NHS Digital. It is required when risks are being identified as part of a workshop. It details the attendees and confirms approval that the set of risks identified are complete and correct and can be used as a template for suppliers to complete.
Guidance on Filling Out the Risk Log
Field/Column Descriptor | To Be Completed by N - NHS Digital S - Supplier F - Formula | Column Type F - Free Text P - Pick List C - Calculated | Additional Information
QMM Threshold | N | P | If the Supplier for whom the Risk Log is being prepared has been assessed for a QMM score - the appropriate value should be selected from the drop-down. If no QMM has been assessed this field should be left at "0".
Programme Risk Threshold | N | P | If the programme has elected to set a risk threshold - the appropriate value should be selected. If not, the field should be left a "0".
Programme Name | F | C | This field will be populated from the RAW Governance (NHS) tab.
Phase | N | P | This field can be used to indicate the phase of the programme to be reviewed.
Risk ID | N* | F | The Unique Identifier for given risk. N* - It is possible that a supplier may identify an unwanted cause and/or effect in which case they should add these to the spreadsheet. If a supplier adds an additional risk then they must append with the abbreviation 'SUPP' E.g. SCR00010SUPP where SCR is a descriptor of the set of risks that has been added to.
Risk Grouping | N* | F | Used to categorise risks by the product component. This will vary according to the product under review. Different types of programme are likely to require different sets of groupings.
Unwanted Effect/Outcome Description | N* | F | Describe the unwanted effect that relates to service/system release being risk assessed.
Primary Area of Impact | N* | P | The area where the impact of the unwanted effect is the greatest.
Primary Impact Rating | N* | P | The Impact rating should the unwanted effect occur. Consider the scale of how bad things could be when identifying the impact, this will ensure consistency across the identified risks. Please use the Impact Scales tab for guidance. If the supplier feels that the impact rating is not appropriate when considering their use of the service then they should select the most appropriate value and highight that this has been changed.
Clinical Risk | N* | P | "Y" if there is a clinical risk associated with this outcome. The risk
Cause | N* | F | Describe the cause or causes that would produce the unwanted effect. There will often be multiple potential causes for each unwanted effect/outcome. There should be a separate line for each cause/effect combination, so that all necessary mitigations can be identified. Even if two impacts would be addressed by the same mitigation,
Cause Likelihood | S* | P | Identify the likelihood of the unwanted effect occurring prior to applying any controls/mitigations. If there are no existing controls in place then the supplier MUST set likelihood to at least a value of 3 (in some cases NHS Digital may identify these and include them already filled out in the template). If NHS Digital can identify this during the original workshop then they may include entries in this cell . A table of likelihood ratings is below on this tab.
Justification of Cause Likelihood Rating | S* | F | Add the rationale for the likelihood score supplied. This could be for example that functionality exists and controls are already in place or that the system does not support functionality to cause the unwanted effect. You must not use the controls you plan to put in place as justification in this cell, this is all about existing controls not future controls or mitigations. If NHS Digital have identified the Cause Likelihood then this will also be completed by NHS Digital.
Overall Risk Score (Pre-Mitigation) | F | C | Overall Risk Score (Pre-Mitigation): This is calculated as Primary Impact Rating x Cause Likelihood. This is the score of the risk prior to the Supplier applying any controls.
Supplier Mitigation detail required? | F | C | If the Overall Risk Score (Pre-Mitigation) is the same or higher than the Programme Risk Threshold displays "Y" to indicate that the Supplier must provide the details of their mitigation plan for the risk.
Supplier Internal Mitigations | S | F | If there is a "Y" in Supplier Mitigation detail required? Column - the Supplier must add the details of the controls that will be put in place to mitigate the unwanted effect and/or its cause.
Post Mitigation Likelihood | S | P | If there is a "Y" in Supplier Mitigation detail required? Column - identify the likelihood of the unwanted effect / cause occurring once controls have been put in place. This will form part of the input into the residual risk score. A table of likelihood interpretations is available further down on this tab.
Residual Score | F | C | A cell using formula to calculate the residual score (Primary Impact Rating x Post Mitigation Likelihood).
In Scope for Assurance ? | F | C | The value (Y/N) is determined by the Overall Risk Score (Pre-Mitigation) when compared to the suppliers QMM rating. If QMM has not been applied within the project then all risks fall within scope of assurance. The value of 'Supplier Mitigation Required' will also determine this value. If set to 'N' then this column value will also be 'N'.
Assigned Assurance Group | N | P | Primarily the assurance activities will be undertaken by SA however there are some assurance activities that will be assigned to other stakeholders or maybe one or more stakeholder. E.g. Training is a programme assurance activity.
High Level Assurance Mitigation | N | P | Select the most suitable option from the Pick List. If there is no suitable match on the list then choose 'Other' and elaborate in the next column. If you feel that there should be additional selections then please email assurance@nhs.net to request that the pick list be updated to include your recommendation.
Elaboration | N | F | Provide further elaboration on the high level assurance action you have identified. E.g. Provide further detail on the witness test activities you wish to undertake. Further detailed elaboration on the specific tasks must be recorded where you are tracking progress.
Is the mitigation in place? | N | P | Confirmation from the NHSD assurer that the mitigation is in place.
N* - Whilst these are, by default, for NHS Digital to complete - it is possible that the supplier may identify an unwanted effect/cause that has not been listed. In this event the Supplier should complete these cells. If there is specific guidance for a supplier to follow for a given cell then this is explicitly stated in the Additional Information section of the table above.
S* - This cell will be completed by the Supplier, by default, however NHS Digital may complete this field during the initial internal workshops. If the supplier feels an NHS Digital entry in this field needs updating then they may do so.
Likelihood Interpretations (Source: DCB0129)
Likelihood Category (Score) | Interpretation
Very high (5) | Certain or almost certain; highly likely to occur
High (4) | Not certain but very possible; reasonably expected to occur in the majority of cases
Medium (3) | Possible
Low (2) | Could occur but in the great majority of occasions will not
Very low (1) | Negligible or nearly negligible possibility of occurring
Assurance Group Interpretations
Group | Interpretation
SA | Solution Assurance will undertake the assurance to mitigate the risk. SME includes Functional Test Assurance, Non-Functional Test Assurance and Data Assurance.
Programme | A programme resource will undertake the assurance to mitigate the risk. SME includes Business Process, System Architecture, Information Governance and Training.
CSG | CSG will undertake assurance to mitigate the identified risk. SME includes assurance to clinical safety standards.
Service Management | Service management will undertake assurance to mitigate the identified risk. SME includes change management, service management, incident management and service readiness.
Cyber Security | Cyber will undertake assurance to mitigate the identified risk. SME includes assurance to system vulnerabilities and evaluation of penetration test reports.
Other | Not defined or a collection of those groups listed above will be required to collaborate in assurance activities.

## Risk Log
QMM Threshold All Risks with Pre-Mitigation Score = or >: |  | 0
| Programme Risk Threshold: | 0
| Programme Name: | Signing Service for Connecting Systems
| Phase: | n/a
|  | Unwanted Effect | [13 empty] | Assurance
Risk Id | Risk Grouping | Unwanted Effect/Outcome Description | Primary Area of Impact | Primary Impact Rating | Clinical Risk (Y/N) | Cause | Cause Likelihood (1-5) | Justification of Cause Likelihood Rating | Overall Risk Score (pre-mitigation) Calculated | Supplier Mitigation detail required? Calculated | Supplier Internal Mitigations | Post Mitigation Likelihood | Residual Score Calculated | In scope for assurance (Y/N) Calculated | Assigned Assurance Group | High Level Assurance Mitigation | Elaboration - Assurance Mitigation Detail | Is the mitigation in place?
SIGSERV-GEN-001 | Authorisation | Signature generated by prescribing system for user without relevant RBAC rights | Clinical | 4 | Y | The prescriber system has not correctly checked whether the user has the correct activity code within RBAC, which dictates whether they're authorised to sign a prescription |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-002 | Signing | Failure to generate a digitally signed prescription | Clinical | 4 | Y | The prescriber system is failing to store the digest returned from the EPS FHIR API |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-003 | Signing | Failure to generate a digitally signed prescription | Clinical | 4 | Y | The prescriber system is not providing a valid signed JWT to SignatureRequest endpoint |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-004 | Signing | Failure to generate a digitally signed prescription | Clinical | 4 | Y | Failure to to establish SignalR connection from inside the Prescribing user's web browser to Signing Service Javascript |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-005 | Signing | Failure to generate a digitally signed prescription | Clinical | 4 | Y | The prescriber system is not providing token to SignatureResponse endpoint |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-006 | Signing | Failure to generate a digitally signed prescription | Clinical | 4 | Y | The prescriber system is failing to store signatures and X509 certificates from SignatureResponse endpoint |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-007 | Signing | Failure to generate a digitally signed prescription | Clinical | 4 | Y | The prescriber system is failing retrieve the stored the digest returned from the EPS FHIR API |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-008 | Signing | Failure to generate a digitally signed prescription | Clinical | 4 | Y | The prescriber system is incorrectly assembling XMLDSIG from the digest, signature and X509 certificate |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-009 | Bulk Signing | Failure to generate a digitally signed prescription | Clinical | 5 | Y | The prescriber system has not implemented limits on volume of prescriptions that can be bulk signed as per specification |  |  | 0 | Y |  |  | 0 | Y
SIGSERV-GEN-010 | Error handling | The prescriber system displays a success message rather than an error message during the signing process such that they think that the prescription has been digitally signed | Clinical | 4 | Y | The prescriber system is failing to process and cascade any error responses to the user |  |  | 0 | Y |  |  | 0 | Y

## Impact Scales
Guidance
You should use the impact scales to derive the Primary Impact Rating of the unwanted effect recorded on the Risk Log tab.
Use the table below to identify the highest Impact Level that contains one or more statements that match the impact of the unwanted effect. This impact level should be used as the Primary Impact Rating.
You are expected to contextualise the statements in the table with the unwanted effect.
Important Note : The clinical impact definitions listed below are taken from DCB0129 and are maintained within that standard. Please ensure there have been no updates to the standard before using the definitions listed below to rate risks where Clinical is the primary area of impact.
| Impact Level 1 | Impact Level 2 | Impact Level 3 | Impact Level 4 | Impact Level 5
Interoperability | Technical issue, no impact to any programme or business objectives or operational goals, no change/workaround required. | Technical issue, resulting in failure to meet programme or business objectives or operational goals, still within acceptable limits, no changes/workaround required | Technical issue, resulting in failure to meet programme or business objectives or operational goals, requiring moderate changes/workaround to accommodate | Technical issue resulting in failure to meet programme or business objectives or operational goals, requiring significant changes/workaround to accommodate | Technical issue resulting in failure to meet programme or business objectives or operational goals, requires significant changes to accommodate, there are no workarounds | Technical/Business and Operational Goals
| Programme or Care Org budget unaffected | Programme or Care Org budget impacted by up to +10% | Programme or Care Org budget impacted by +11-50% | Programme or Care Org budget impacted by +51-100% | Programme or Care Org budget impacted by >100% | Cost
| No programme delay, outside planned contingency or workarounds | Programme delay by up to +10% on plan | Programme delay by +11-50% on plan | Programme delay by +51-100% on plan | Programme delay by >100% on plan | Schedule
Usability | Usability issue, the problem is rare and causes minimal loss of time. Minor cosmetic or consistency issue | Usability issue, a minor but irritating problem. Generally, it slows users down slightly. There are minimal violations of guidelines that affect appearance or perception, and mistakes that are recoverable | Usability, a moderate problem causing time to be wasted. There is a workaround to the problem. Internal inconsistencies result in increased learning or error rates. An important function or feature does not work as expected | Usability issue, a severe problem for which the user has no workaround to the problem resulting in a lot of time being wasted | Usability issue resulting in the occurrence of catastrophic errors. The problem could result in large-scale failures that prevent many people from doing their work. Performance is so bad that the system cannot accomplish business goals | Quality
| Accessibility issue, no impact on accessibility requirements, no change/workaround required. | Accessibility issue, resulting in failure to meet highest level of achievement against accessibility requirements, still within acceptable limits, no changes/workaround required | Accessibility issue, resulting in failure to meet minimum level of accessibility requirements, requires moderate changes/workaround to accommodate | Accessibility issue, resulting in failure to meet minimum level of accessibility requirements, requiring significant changes/workaround to accommodate | Accessibility issue, resulting in failure to meet minimum level of accessibility requirements, requires significant changes to accommodate, there are no workarounds | Quality
| Programme or Care Org budget unaffected | Programme or Care Org budget impacted by up to +10% | Programme or Care Org budget impacted by +11-50% | Programme or Care Org budget impacted by +51-100% | Programme or Care Org budget impacted by >100% | Cost
| Users remain happy with the system | Users will be slightly irritated by the problem. | Users will become unsatisfied with the system. | User will be expecting problems to occur thus causing reputational damage | The user is unable or unwilling to use the system. Complete dissatisfaction. | Reputation
| No programme delay, outside planned contingency or workarounds | Programme delay by up to +10% on plan | Programme delay by +11-50% on plan | Programme delay by +51-100% on plan | Programme delay by >100% on plan | Schedule
Data Quality | Localised minor data quality issue, no impact to any programme or business objectives or operational goals, no change/workaround required | Localised minor data quality issue, resulting in failure to meet programme or business objectives or operational goals, still within acceptable limits, no changes/workaround required | Localised moderate data quality issue, resulting in failure to meet programme or business objectives or operational goals, requiring minor changes/workaround to accommodate | Localised significant data quality issue, resulting in failure to meet programme or business objectives or operational goals, requiring extensive changes/workaround to accommodate | Data quality issue affecting centrally stored data or data consumed by other systems resulting in failure to meet programme or business objectives or operational goals, requires change/workaround to accommodate | Data Quality/Business and Operational Goals
| Programme or Care Org budget unaffected | Programme or Care Org budget impacted by up to +10% | Programme or Care Org budget impacted by +11-50% | Programme or Care Org budget impacted by +51-100% | Programme or Care Org budget impacted by >100% | Cost
| No programme delay, outside planned contingency or workarounds | Programme delay by up to +10% on plan | Programme delay by +11-50% on plan | Programme delay by +51-100% on plan | Programme delay by >100% on plan | Schedule
Clinical Safety | [5 empty] | Taken from DCB0129
| Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible severity - Single | Minor injury or injuries from which recovery is not expected in the short term - Single | Severe injury or severe incapacity from which recovery is expected in the short term - Single | Death - Single | Death - Multiple
|  | Significant psychological trauma - Single | Severe psychological trauma - Single | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term - Single | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term - Multiple
|  | Minor injury from which recovery is expected in the short term - Multiple | Minor injury or injuries from which recovery is not expected in the short term - Multiple | Severe injury or severe incapacity from which recovery is expected in the short term - Multiple
|  | Minor psychological upset; inconvenience - Multiple | Significant psychological trauma - Multiple | Severe psychological trauma - Multiple
National Systems | Technical issue or unsupported functionality, no impact to any programme or business objectives or operational goals, no change/workaround required to any National Systems | Technical issue or unsupported functionality, resulting in failure to meet programme or business objectives or operational goals, still within acceptable limits, no changes/workaround required within the relevant National System | Technical issue or unsupported functionality, resulting in failure to meet programme or business objectives or operational goals, minor changes/workaround required to one or more of the National Systems | Technical issue or unsupported functionality, resulting in failure to meet programme or business objectives or operational goals, moderate changes/workaround required to one or more of the National Systems | Technical issue or unsupported functionality, resulting in failure to meet programme or business objectives or operational goals, significant change(s) required to one or more of the National Systems. No workaround available | Technical/Business and Operational Goals
| Programme or Care Org budget unaffected | Programme or Care Org budget impacted by up to +10% | Programme or Care Org budget impacted by +11-50% | Programme or Care Org budget impacted by +51-100% | Programme or Care Org budget impacted by >100% | Cost
| No programme delay, outside planned contingency or workarounds | Programme delay by up to +10% on plan | Programme delay by +11-50% on plan | Programme delay by +51-100% on plan | Programme delay by >100% on plan | Schedule
National Datasets (Secondary Uses) | Minor technical or data quality issue, no impact to any programme or business objectives or operational goals, no change/workaround required for secondary use of the dataset | Minor technical or data quality issue, resulting in failure to meet programme or business objectives or operational goals, still within acceptable limits, no changes/workaround required for secondary use of the dataset | Moderate technical or data quality issue, resulting in failure to meet programme or business objectives or operational goals, requiring minor changes/workaround prior to secondary use of the dataset | Significant technical or data quality issue, resulting in failure to meet programme or business objectives or operational goals, requiring extensive changes/workaround prior to secondary use of the dataset | Catastrophic technical or data quality issue, resulting in failure to meet programme or business objectives or operational goals, no change/workaround available. Unable to use the dataset for secondary uses | Data Quality/Business and Operational Goals
| Programme or Care Org budget unaffected | Programme or Care Org budget impacted by up to +10% | Programme or Care Org budget impacted by +11-50% | Programme or Care Org budget impacted by +51-100% | Programme or Care Org budget impacted by >100% | Cost
| No programme delay, outside planned contingency or workarounds | Programme delay by up to +10% on plan | Programme delay by +11-50% on plan | Programme delay by +51-100% on plan | Programme delay by >100% on plan | Schedule
IG | Breach of confidentiality for personal data, only a single data subject affected. | Breach of confidentiality for personal data <10 data subjects impacted | Breach of confidentiality for personal data <50 data subjects impacted | Breach of confidentiality for personal data for up to 100 data subjects impacted OR Breach of confidentiality for sensitive personal data for single data subject | Breach of confidentiality for personal data for up to 1000 data subjects impacted OR Breach of confidentiality for sensitive personal data for more than a single data subject | Confidentiality
| Minor data integrity ssue, no impact to any programme or business objectives or operational goals, no change/workaround required. | Minor data integrity issue, resulting in failure to meet programme or business objectives or operational goals, still within acceptable limits, no changes/workaround required. | Moderate data integrity issue, resulting in failure to meet programme or business objectives or operational goals, requiring minor changes/workaround. | Significant data integrity issue, resulting in failure to meet programme or business objectives or operational goals, requiring significant changes/workaround to accommodate | Catastrophic data integrity issue, resulting in failure to meet programme or business objectives or operational goals, requires significant changes to accommodate, there are no workarounds | Integrity
| Minor availability issue, no impact to any programme or business objectives or operational goals, | Minor availability issue, still within acceptable limits and not impacting stakeholders | Moderate availability issue, impacting stakeholders, service still within acceptable limits | Significant availabilityy issue, bringing considerable inconvience to stakeholders, resulting in failure to meet programme or business objectives or operational goals. | Catastrophic availability issue, bringing unacceptable inconvience to stakeholders, resulting in failure to meet programme or business objectives or operational goals. | Availability
| Programme or Care Org budget unaffected | Programme or Care Org budget impacted by up to +10% | Programme or Care Org budget impacted by +11-50% | Programme or Care Org budget impacted by +51-100% | Programme or Care Org budget impacted by >100% | Cost
| No programme delay, outside planned contingency or workarounds | Programme delay by up to +10% on plan | Programme delay by +11-50% on plan | Programme delay by +51-100% on plan | Programme delay by >100% on plan | Schedule
System/Solution Integrity | System/solution performance issue or technical issue related to management of system integrity, no impact to any programme or business objectives or operational goals, no change/workaround required. | System/solution performance issue or technical issue related to management of system integrity, resulting in failure to meet programme or business objectives or operational goals, still within acceptable limits, no changes/workaround required | System/solution performance issue or technical issue related to management of system integrity, resulting in failure to meet programme or business objectives or operational goals, requiring moderate changes/workaround to accommodate | System/solution performance issue or technical issue related to management of system integrity, resulting in failure to meet programme or business objectives or operational goals, requiring significant changes/workaround to accommodate | System/solution performance issue or technical issue related to management of system integrity, resulting in failure to meet programme or business objectives or operational goals, requires significant changes to accommodate, there are no workarounds | Technical/Business and Operational Goals
| Programme or Care Org budget unaffected | Programme or Care Org budget impacted by up to +10% | Programme or Care Org budget impacted by +11-50% | Programme or Care Org budget impacted by +51-100% | Programme or Care Org budget impacted by >100% | Cost
| No programme delay, outside planned contingency or workarounds | Programme delay by up to +10% on plan | Programme delay by +11-50% on plan | Programme delay by +51-100% on plan | Programme delay by >100% on plan | Schedule
Cyber Security | Vulnerability discovered. Rated Low, remediation unlikely, mitigation provided. Residual risk accepted. | Vulnerability discovered. Rated Medium, remediation unlikely, mitigation / workaround established. Residual risk accepted for private & public beta, but long term solution required. | Vulnerability discovered. Rated High, remediation unlikely in the short term, mitigation / workaround established. Residual risk accepted only for private beta, long term solution required before public beta. | Vulnerability discovered. Rated High / Critical, remediation unlikely in the short term, mitigation / workaround not sufficient. Residual risk not accepted for private beta until quick fix is provided in lieu of a long term solution. | Vulnerability discovered. Rated High / Critical, remediation unlikely in the short term, no adequate mitigation / workaround. No way forward until solution developed.

## Metrics
Total No. of Risks | 10
SEVERITY
5 | 1
4 | 9
3 | 0
2 | 0
1 | 0
NOT CLASSIFIED | 0
PRIMARY AREA OF IMPACT
Clinical | 10
Data Quality | 0
IG | 0
Interoperability | 0
National Datasets | 0
National Services | 0
Usability | 0
NOT CLASSIFIED | 0
PRE-MITIGATION SCORE
Between 1 and 3 | 0
Between 4 and 7 | 0
Between 8 and 14 | 0
Between 15 and 19 | 0
Between 20 and 25 | 0
NOT CLASSIFIED | 10
POST-MITIGATION SCORE
Between 1 and 3 | 0
Between 4 and 7 | 0
Between 8 and 14 | 0
Between 15 and 19 | 0
Between 20 and 25 | 0
>15 | 0 | Needs to be zero for Beta
>10 | 0 | Needs to be zero for Go-Live
NOT CLASSIFIED | 10