## Cover Page
Clinical Safety Hazard Log - FHIR PDS API - API Platform
Programme | Digital Interopability Platform | Document Record ID Key
Sub-Prog / Project | API Platform | API Platform: FHIR PDS-HL-02 (superceding NPFIT-FNT-TO-TOCLNSA-2194)
Prog. Director |  | Status | Approved
Owner | Raman Behl | Version | 4
Author | Sean White | Version Date | 2020-12-18
Clinical Safety Hazard Log - FHIR PDS API - API Platform
Copyright © 2018, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.

## Version History
Amendment History
Version | Date | Amendment History
0.1 |  | First draft Hazard Log
1 | 2020-03-18 | Release for approval PDS Read Only
2 | 2020-07-24 | Release of PDS Update
2.1 | 2020-11-09 | Assurance of system restricted authentication model for PDS Read only
3 | 2020-12-18 | Formal issue following review and provision of evidence.
5 | 2022-04-28 | Rlease of PDS FHIR API citizen update
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Chris Dickson |  | CSO | 2020-03-16 | 1
Raman Behl |  | CSO | 2020-03-18 | 1
Munish Jokhani |  | Project manager | 2020-03-18 | 1
Chris Dickson |  | CSO | 2020-03-24 | 2
Raman Behl |  | CSO | N/A | 2
Munish Jokhani |  | Project manager | 2020-03-24 | 2
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Chris Dickson |  | CSO | 2020-03-16 | 1
Raman Behl |  | CSO | 2020-03-18 | 1
Munish Jokhani |  | Project manager | 2020-03-18 | 1
Chris Dickson |  | CSO | 2020-03-24 | 2
Raman Behl |  | CSO | N/A | 2
Munish Jokhani |  | Project manager | 2020-03-24 | 2
Raman Behl |  | CSO | 2020-12-18 | 3
Raman Behl |  | CSO | 2021-01-14 | 4
Raman Behl |  | CSO | 2022-04-28 | 5
Distribution
NHS Digital Clinical Safety Personnel
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## FHIR PDS Read Only Hazard Log
|  | Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[6 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PDSRO1 | 2020-02-13 | False positive PDS search result returned (single result). On going care compromised due to wrong PDS information returned, impacting ability to 1. Use correct NHS Number 2. Send correspondance to target patient 'A' (Patient B sent Patient A's comms, Patient A sent nothing). 3. Access wrong information / services e.g. SCR, ERS 4. Access the wrong patient medical record a. Clinical decision based on wrong information b. Creation of confused record - Patient A's clinical information could be recorded within patient B' Electronic Clinical Record | Wrong Patient PDS record returned | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Potential delay to Patient care | Field mapping of request data to PDS query is incorrect | N/A | N/A | N/A | N/A | N/A | N/A | Significant | Medium | 2 | From previous experience | https://jira.digital.nhs.uk/browse/APM-6 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | N/A | N/A | N/A | N/A | Significant | Very Low | 1 | Based on confidence gained through additional controls | API Management | Open
[5 empty] | Truncation of data performed by PDS API | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-6 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | Documentation to provide description of how to use search | https://emea-demo8-nhsdportal.apigee.io/docs/patients-sandbox/1/routes/Patient/get | Code review by IOPS and Spine | https://github.com/NHSDigital/personal-demographics-service-api/pulls?q=is%3Apr+
[5 empty] | Translation of flags from inbound request to PDS query within PDS API is incorrect e.g. Historic data match. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-12 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | Documentation to provide description of how to use search | https://emea-demo8-nhsdportal.apigee.io/docs/patients-sandbox/1/routes/Patient/get | Code review by developer and architecture and Spine, verified with user research | https://github.com/NHSDigital/personal-demographics-service-api/pulls?q=is%3Apr+
[5 empty] | Incorrect handling of wildcard flag in the PDS API | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-12 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | Documentation to provide description of how to use search | https://emea-demo8-nhsdportal.apigee.io/docs/patients-sandbox/1/routes/Patient/get | Code review by developer and architecture and Spine, verified with user research | https://github.com/NHSDigital/personal-demographics-service-api/pulls?q=is%3Apr+
[5 empty] | Incorrect handling of special characters in the PDS API | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-100 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | Documentation to provide description of how to use search | https://emea-demo8-nhsdportal.apigee.io/docs/patients-sandbox/1/routes/Patient/get | Code review by developer and architecture and Spine, verified with user research | https://github.com/NHSDigital/personal-demographics-service-api/pulls?q=is%3Apr+
[5 empty] | Truncation of PDS results within PDS API is not the correct set specified by the connected system i.e. System requests up to 30 matches and 40 are returned. | There are maximum of 50 results allowed | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-100 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | Documentation to provide description of how to use search | https://emea-demo8-nhsdportal.apigee.io/docs/patients-sandbox/1/routes/Patient/get | N/A | N/A
[5 empty] | Failure to correctly map result data from PDS in PDS API | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-9 https://jira.digital.nhs.uk/browse/APM-12 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | N/A | N/A | N/A | N/A
[5 empty] | PDS API truncates patient data within results returned from PDS | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-4 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | Documentation to provide description of how to use search | https://emea-demo8-nhsdportal.apigee.io/docs/patients-sandbox/1/routes/Patient/get | Code review by IOPS and Spine | https://github.com/NHSDigital/personal-demographics-service-api/pulls?q=is%3Apr+
[5 empty] | Weighting isn't applied prior to truncation of result set (High weighting score results excluded from data returned to connected system) | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APMSPII-9 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | N/A | N/A | N/A | N/A
PDSRO2 | 2020-02-13 | False negative PDS search result returned (single result). On going care compromised due to lack of PDS information, adversely impacting ability to 1. Confirm NHS Number 2. Send correspondance to patient 3. Access other services e.g. SCR, ERS | No Patient PDS record returned where one exists | Potential delay to Patient care Could lead to creation of duplicate record | Data quality issue in PDS database | Existing spine controls | Links | N/A | N/A | N/A | N/A | Significant | Low | 2 | From previous experience | N/A | N/A | N/A | N/A | N/A | N/A | Significant | Low | 2 | Existing Controls | API Management and Connecting systems | Transferred
[5 empty] | User Error in search criteria entry/search criteria constrained such as gender free search performed | Response code generation and handling Testing against baseline database of duplicate records ? Technical / Implemenation guidance | N/A | Health professionals are trained by health organisations to search correctly | N/A | N/A | N/A |  |  |  |  | N/A | N/A | Third party suppliers to train users on their User Interface | Moves to SCAL
[5 empty] | Regression of PDS API Proxy due to the introduction of Apllication restricted access FHIR API on the platform |  | APM SPII-4 Acces to and fucntionaility of retrive retrieve JIRA APM - 6, APM -13
[5 empty] | Application Restricted PDS API returns multiple results from PDS Search end point. |  | JIRA ticket APM-1590 | [12 empty] | N/A | N/A
PDSRO3 | 2020-02-13 | Multiple PDS search results returned for user to view and select the correct record. On going care compromised due to wrong selection of PDS information, impacting ability to 1. Use INcorrect NHS Number 2. Send correspondance to target patient 'A' (Patient B sent Patient A's comms, Patient A sent nothing). 3. Access wrong information / services e.g. SCR, ERS 4. Access the wrong patient medical record a. Clinical decision based on wrong information b. Creation of confused record - Patient A's clinical information could be recorded within patient B' Electronic Clinical Record | Wrong selection of Patient PDS record | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Potential delay to Patient care | User error: Accidental selection, Selecting closest match(wrongly), not fully checking | N/A | N/A | Review existing guidance on algorithimic PDS search and weighted results and how thery are displayed to the user | N/A | N/A | N/A | Significant | Medium | 2 | From previous experience | N/A | N/A | Third party suppliers to train users on their User Inreface | Moves to SCAL | N/A | N/A | Significant | Medium | 2 | Existing Controls and controls to be applied by third parties | API Management and Connecting systems | Transferred
PDSRO4 | 2020-03-06 | Valid user (authorised ) and/or system fails to authenticate and / or authentication is delayed and/or authorise and therefore cannot retrieve patient details which impacts subsequent care. | No Patient PDS record returned as Service can’t be accessed | Potential delay to Patient care | API platform Authentication check for PDS API has a fault. Invalid Token (APP-RESTRICTED-PDS-004) | Error messages are generated and guidance is provided by API platform team for interpretataion and suggested actions. | APM-1541 (awaiting approval from security lead on completion of PEN testing) | N/A | N/A | N/A | N/A | Significant | Low | 2 | Non-availability of PDS information | https://jira.digital.nhs.uk/browse/APM-371 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | N/A | N/A | N/A | N/A | Significant | Low | 2 | Additional controls | API Management | Open
[5 empty] | Issue between Spine and API Platform | Error messages are generated and guidance is provided by API platform team for interpretataion and suggested actions. | AMB-51/52/60 APM 1143. Further monitoring to be completed duing private beta for the API. | N/A | N/A | N/A | N/A |  |  |  |  | https://jira.digital.nhs.uk/browse/APM-228 | Test suite has 919 Tests for the PDS API . 912 passes and 7 failures. the failures will be fixed by 24th March, 2020, please see screenshots for evidence | N/A | N/A | N/A | N/A
[5 empty] | Calling application authentication/configuration failure (Responbility of calling application to ensure monitoring is effective, APIM team provides monitoring at platform level not at external application level ) | Technical guidance available and published Test conformance as per requirements/SCAL | SCAL document in development (Architecture TAB)
[5 empty] | Transaction volume exceeds tolerable volumetrics | Volumetrics and performance testing Service availbility of Google cloud hosted Apigee system API platform provides meanigful feedback to wait and try during periuods of high demand Monitoring of volume at platform level to take appropriate action where posiible depending upon scenario leading to high traffic on platform | JIRA APM-1553 to prove volumetrics upto 200 TPS. A threshold limit has been setup at 130 TPS in prod.This was assured via JIRA ticket APM-620
[5 empty] | Cybersecurity: Vulnerability in oAuth end point | Design review/approval by cybersecurity team Pen testing | SA Test Assurance Statement - Application Restricted FHIR PDS API - Technical go-Live v1.2
[5 empty] | API Platform unavailable due to Proxy is not configured appropriately. Failed build error when integrating 3rd party API with the platform | Assurance / Conformance testing requirements for testing of PDS FHIR API prior to deployement onto platform, is proven during PTL | JIRA APM 1478/1529
[5 empty] | Regression of Authentication endpoint, due to introduction of Apllication restricted API on the platform |  | APM SPII-4

## FHIR PDS update Only
|  | Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[7 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | SA Risk log reference *for admin purpose only* | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PDSU1 | 2020-06-18 | User is informed of failure with correct error code | Clincian unable to update PDS record of a patient. | Patient identification compromised resulting in delays in accessing patient care records e.g. demographics is | Google platform proxy error. 1. Google - Apigee platform failure 2. NHSD - Apigee proxy configuration error | A new vulnerability is exploited | Googles COTS service design 99.9% availability | Enterprise level at https://confluence.digital.nhs.uk/display/APM/Security+architecture?preview=%2F97760756%2F108286979%2FApigeeEdgeCloud_user_SpecSheet.pdf | Path to live process | key operating procedure ref: https://confluence.digital.nhs.uk/display/APM/APIM+Key+Operating+Procedures | Path to live process | key operating procedure ref: https://confluence.digital.nhs.uk/display/APM/APIM+Key+Operating+Procedures | Significant | Medium | 2 | From previous experience as much of the process is already established and in live for many years | N/A | N/A | N/A | N/A | N/A | N/A | Significant | Medium | 2 | Initial risk score within acceptable limits so no additional controls are requuired
|  | User is not informed of failure |  | Possibility of patient being missed from an extract/report requested by a customer which could lead to patient screening being missed or delayed. | API Technical failure |  | Designed to comply with FHIR standards Design processes | Iops confirmation Markus Fearnett |  |  | QA built into Jira workflow | https://jira.digital.nhs.uk/projects/APMSPII/issues/APMSPII-118?filter=allopenissues |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
|  | An attempt to make a pds update is rejected however the reason for rejection is not accuratley relayed to the client, |  | Communications to patient sent to wrong destination e.g. address, email, telephone | The management of access to PDS Functionality is not scalable |  | Googles COTS service design Monitoring by Google and NHSD | SLA: Enterprise level at https://confluence.digital.nhs.uk/display/APM/Security+architecture?preview=%2F97760756%2F108286979%2FApigeeEdgeCloud_user_SpecSheet.pdf Monitoring: https://confluence.digital.nhs.uk/display/APM/Monitoring |  |  | Manual On-boarding process sufficient during FOT | https://confluence.digital.nhs.uk/pages/viewpage.action?pageId=108278651 |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
|  | Demographic information related to the patient record becomes out of date, incomplete or corrupt. |  |  | Performance degrades to the extent that is impacts patient care. |  | Googles COTS service performance Monitoring by Google and NHSD via splunk | SLA: Enterprise level at https://confluence.digital.nhs.uk/display/APM/Security+architecture?preview=%2F97760756%2F108286979%2FApigeeEdgeCloud_user_SpecSheet.pdf Performance monitoring: https://confluence.digital.nhs.uk/display/APM/Monitoring |  |  | During FOT deployment is limited therefore demand is controled | https://confluence.digital.nhs.uk/pages/viewpage.action?pageId=108278650
|  | PDS Record can not be accurately updated |  |  | Application Restricted PDS API returns multiple results from PDS Search end point. Regression of PDS API Proxy due to introduction of Apllication restrictes API on the platform | [11 empty] | N/A | N/A | N/A | N/A | N/A | N/A
PDSU2 | 2020-06-18 | Patients PDS data contains incorrect data | (Client) Clinician or Patient attempts to make a pds update which should be rejected but is successful | Patient identification compromised resulting in delays in accessing patient care records e.g. demographics, pharmacist, mobile number etc which should fail validation ( as required in those circumstances, in line with rules) can result in clinical harm resulting due to PDS information being inaccurate/out of date. | Incorrect implementation of validation rules | Client attempts to make a pds update which should be rejected but is successful | Common business logic layer in Spine being re-used i.e. existing PDS validation logic. | See: Logical Architecture at https://confluence.digital.nhs.uk/pages/viewpage.action?pageId=100343566 In live use since Spine II go-live. Add test evidence |  |  |  |  | Major | Very Low | 2 | From previous experience as much of the process is already established and in live for many years | N/A | N/A | N/A | N/A | N/A | N/A | Major | Very Low | 2 | Initial risk score within acceptable limits so no additional controls are requuired
|  |  |  | Possibility of patient being missed from an extract/report requested by a customer which could lead to patient screening being missed or delayed. | User input |  | Common business logic layer in Spine being re-used i.e. existing PDS validation logic. | See: Logical Architecture at https://confluence.digital.nhs.uk/pages/viewpage.action?pageId=100343566 In live use since Spine II go-live. Add test evidence | API documentation covers dev and implementation PDS service requirements persist. | ref SCAL for PDS FHIR API | PDS service business processes persist | https://digital.nhs.uk/services/demographics |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | Communications to patient sent to wrong destination e.g. address, email, telephone | Status flags Date of death, Sensitive flag, applied incorrectly [user error / message error / corruption] Design to be confirmed Post code look up? |  | Common business logic layer in Spine being re-used i.e. existing PDS validation logic. | See: Logical Architecture at https://confluence.digital.nhs.uk/pages/viewpage.action?pageId=100343566 | [8 empty] | N/A | N/A | N/A | N/A | N/A | N/A
PDSU3 | 2020-06-18 | Patient has more than one electronic record neither one containing a complete or current medical history | Duplicate Patient Record exists potentailly adversly affecting care decisions | Potential for inappropriate treatment as demographic and clinical information may reside over two or more records. Possibility of patient being erroneously excluded/added from/to an extract/report requested by a customer which could lead to patient screening being missed / delayed or wrongly assigned. | Trace / query interaction not functioning correctly. User unable to find existing record meaning a new registration is created on Local System. |  | Common business logic layer in Spine being re-used i.e. existing PDS validation logic. This api can only update existing record can not creat e new | See: Logical Architecture at https://confluence.digital.nhs.uk/pages/viewpage.action?pageId=100343566 | [8 empty] | N/A | N/A | N/A | N/A | N/A | N/A
[5 empty] | PDS record verification unsuccessful meaning a new registration on PDS is created in error i.e. Patient has two NHS numbers created. |  | Common business logic layer in Spine being re-used i.e. existing PDS validation logic. This api can only update existing record can not creat e new | See: Logical Architecture at https://confluence.digital.nhs.uk/pages/viewpage.action?pageId=100343566 |  |  | National back office process to resolve reported issues AND active management of duplicates | long established process | Major | Very Low | 2 | From previous experience as much of the process is already established and in live for many years | N/A | N/A | N/A | N/A | N/A | N/A | Major | Very Low | 2 | Initial risk score within acceptable limits so no additional controls are requuired

## FHIR PDS Citizen Update
|  | Hazard Assessment |  |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Date Added | Hazard Description |  |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[7 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
|  | Effect | Hazard | Harm | Possible Causes | SA Risk log reference *for admin purpose only* | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PDSCU1 | 2022-04-22 | Users of the API Platform are experiencing problems when attempting to use one of the APIs hosted on there | Citizen unable to access PDS record | Potential patient inconvenience as patient unable to view, set/update correct details. | Degradation of performance due to increase traffic introduced by Patient Access | [7 empty] | Significant | Low | 2 |  |  | https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1174 https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1218 https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1226 https://nhsd-jira.digital.nhs.uk/browse/SPII-35183 |  |  |  |  | Significant | Very Low | 1 | Initial risk score within acceptable limits so no additional controls are required
|  | Unable to use PDS FHIR API |  |  | Degradation of performance due to increase traffic introduced by Patient Access (NFT team )
|  | Incorrect error message is displayed when unauthorised action takes place (Any Validation) for patient |  |  | Failure of the API to generate correct error response to relay back to end user
|  | Patient unable to read their own details |  |  | Incorrect validation in the PDS FHIR API
|  | Current users is unable to access the PDS FHIR API |  |  | The regression issue introduced through development PDSFHIRAPI for patient access
PDSCU2 | 2022-04-22 | Users of the API Platform are experiencing problems when attempting to use one of the APIs hosted on there | Citizen Unable to update their patient record | Potential delay to patient care as patient unable to set/update correct details. | Degradation of performance due to increase traffic introduced by Patient Access | [7 empty] | Major | Low | 3 |  |  | https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1174 https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1218 https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1226 https://nhsd-jira.digital.nhs.uk/browse/SPII-35183 |  |  |  |  | Major | Very Low | 2 | The Initial assessment of this hazard and impact evaluation has been based upon a existing hazard evaluation of EPS FHIR API Hazard 2, as an example. The actual clinical impact evaluation will vary from Usecase to Usecase. A supplier/service integrating with PDS FHIR API are strongly recommended to review the hazard in the context of their Usecase/service design and perform appropriate mitigation activities to manage the clinical risk.
|  | Unable to use PDS FHIR API |  | Potential patient inconvenience as patient unable to view, set/update correct details. | Degradation of performance due to increase traffic introduced by Patient Access (NFT team )
|  | Incorrect error message is displayed when unauthorised action takes place (Any Validation) for patient |  | Communications to patient sent to wrong destination e.g. address, email, telephone, Nominated pharmacy | Failure of the API to generate correct error response to relay back to end user
|  | Patient unable to read their own details |  |  | Incorrect validation in the PDS FHIR API
|  | Current users is unable to access the PDS FHIR API |  |  | The regression issue introduced through development PDSFHIRAPI for patient access
|  | Patient is not able to update details which they are permitted to do so |  |  | Incorrect validation in the PDS FHIR API
|  | Patient updates are failing |  |  | Failing to format header correctly
PDSCU3 | 2022-04-22 | Unauthorised access to the PDS | Wrong citizen /patient record updated | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Communications to patient sent to wrong destination e.g. address, email, telephone, Nominated pharmacy Potential delay to Patient care | Development for patient access has introduced to vulnerability |  | https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1163 https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1218 | [10 empty] | https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1163 https://nhsd-jira.digital.nhs.uk/browse/APMSPII-1218
|  | Patient is able to update details for which they don’t have permission to do so |  |  | Allowed to read a record other than that identified via NHS Login (different NHS No. to the one identified at auth) Failure in delegation logic | [7 empty] | Major | Low | 3 | [7 empty] | Major | Very Low | 2 | The Initial assessment of this hazard and impact evaluation has been based upon a existing hazard evaluation of EPS FHIR API Hazard 2, as an example. The actual clinical impact evaluation will vary from Usecase to Usecase. A supplier/service integrating with PDS FHIR API are strongly recommended to review the hazard in the context of their Usecase/service design and perform appropriate mitigation activities to manage the clinical risk.

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required

## References
Reference | Description | Version | Doc. No.
1 | DDC API management team / SA Risk log |  | https://hscic365.sharepoint.com/:x:/s/APIManagement/Ec0NMqxPD9tHpvMg0CKG52YB8rRwxwM2dMzP92oVye2rww?e=86gjQR
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16