## Slide 1
Task | IG Manager | IT Manager | Information security team | Information governance (IG) team | Senior Information Risk Owner (SIRO) | Data protection officer (DPO) | Procurement | Caldicott Guardians | Executive Directors | Wider Organisation
Collect documentation for each principle to be assessed |  |  | R | R | A | A | C |  |  | I
Discuss and agree current position of each outcome (Achieved, Partially Achieved, Not Achieved) |  |  | R | R | A | A | C | I | I | 
Agree terms of reference and timelines for the assessment | R | R | C | C | A | A |  | I | I | 
Communicate assessment timelines with departments | R | R |  |  | A | A |  |  |  | I
Kick-off call | R | R |  |  | A | A |  | I | I | 
Arrange fieldwork meetings | R | R |  |  | A | A |  | C |  | 
Send documents to assessors |  |  | R | R | A | A |  | C | C | 
Take part in fieldwork meetings and collate additional documents | R | R | C | C | A | R |  | R |  | 
Close-out call | R | R |  |  | A | A |  | I | I | 
Read and discuss draft report | R | R |  |  | R A | R |  | R | I | 
Agree action owners and timelines | R | R |  |  | R A | R |  | R |  | 
Provide management responses | R | R |  |  | A | I |  | I | I | 
Read and agree final report | R | R |  |  | R C | R |  | R | I | 
Create action plan for remediation of findings | R | R |  |  | R A | R |  | R | C | 
Add assessors to the toolkit | R |  |  |  | A | I |  |  | I | 
Submit final report to NHS England (NHSE) | I | I |  |  | R A | I |  | I | I | 
Present final report to audit committee | I | I |  |  | R | I |  | I | I | 
Ongoing reporting of progress to audit committee |  |  |  |  | R A | I |  | I | I | 
Key R Responsible A Accountable C Consulted I Informed |  |  |  |  |  |  |  |  |  | 
Appendix A – Organisational RACI