## Cover
Third-party application review
This is a guide in helping a GP Practice identify all its third-party applications that will need to be reviewed to ensure a seamless transition between two foundation systems and provide discussion around mitigations.
Using this checklist
The checklist is fully editable. If you want to make more space in a row, place your cursor in the row and press Enter.
If you want to edit the tables, you can right click on the table and choose Insert or Delete to add or remove columns or rows.
After downloading this checklist, it is good practice to check periodically for updates to the guide and checklist.
This checklist was last updated on 02/12/2025
Objective
This review should evaluate all third-party systems that will be impacted by the new clinical system. By identifying all impacted third-party systems and reviewing with stakeholders everyone should be clear on the impact and any mitigations necessary to allow for a seamless transition.
This should be a living document and updated reguarly
Who is involved
The people, teams or organisations who might be required in this stage of the migration are:
· GP practice stakeholders
o practice manager
o practice staff
o lead GP
· new GP system supplier
· community services
· commissioning support unit (CSU)/IT support provider
· integrated care board (ICB)
· palliative hospice/hospice at home

## 3rdPartyApps
System Name | Purpose | Owner/Contact | Compatible with new system? | Notes | RAG
e.g. DocMate | Filing and editing of documents onto the system | Dave | No | New system has document management that meets our requirements so no longer necessary, but need to make sure all documents migrate from DocMate
e.g. QOFHelper | Runs reports to identify patients who potential need recalls/intervention for maximising QOF points | Sarah | Yes | Confirmed QOFHelper is compatible with the new GP Clinical System