## 21.04.2021
Faster SUS+ program
Tom to evaluate value of unfinished episode submissions once the data is available to his team. If it is deemed worthwhile, benefits will be brought back to the group.
CDS6.3 update
CDS6.3 will keep MH and maternity data items
Expectation is everyone to be on CDS6.3 by April 2023
Discussion re reliability of the burden assessment estimates given low response rate and incorporation of other workings
Casemix DQ of SUS+ data
Spikes in U grouping for private sector providers
Spire and Casemix to review data outside the meeting
SUS+ Service Update
availability SLA hit but SUS+ is doing more work for covid requirments and daily deltas for DSCROs
SUS+ Product Update
SUS+ to implement 21/22 grouper, pss and consultation tariff by end of April 2021
AOB

## 19.05.2021
Faster SUS+ program
CCG issue of not receiving weekly APC or OP data from DSCROs
All DSCRO issues need to be sent to dsfcliveservice@nhs.net
CDS6.3 update
ISN expected to be published 15/06/2021
CDS6.3 go-live April 2022
Expect everyone to be off CDS6.2 by April 2023
SUS+ Service Update
RIAK AAE tree rebuild during inclusion deadlettered a number of extracts and meant increased processing time
SUS+ Product Update
AHAS replacement for HES, development ongoing
SUS+ now has 4 pandemic data feeds (PHE, MHRA, Edge, Oxford)
AOB
2021-05-01 | 60 day activity date range extracts min
Code | Name | extract | extract | extract
0CM | DSCRO NORTH OF ENGLAND | pbr_apc_episodes_bundle | pbr_em_011_backward_compatible_bundle | pbr_op_bundle
0CN | DSCRO SOUTH WEST | pbr_apc_episodes_bundle | pbr_em_011_backward_compatible_bundle | pbr_op_bundle
0CP | DSCRO CENTRAL MIDLANDS | pbr_apc_episodes_bundle | pbr_em_011_backward_compatible_bundle | pbr_op_bundle
0CT | DSCRO NORTH AND EAST LONDON | pbr_apc_episodes_bundle | pbr_em_011_backward_compatible_bundle | pbr_op_bundle
0CV | DSCRO NORTH WEST | pbr_apc_episodes_bundle | pbr_em_011_backward_compatible_bundle | pbr_op_bundle

## 16.06.2021
Faster SUS+ program
Update soon about unfinished episodes data
CDS6.3 update
ISN published 15/06/2021
XML schema expected to be published September 2021
CDS6.3 go-live April 2022
Expect everyone to be off CDS6.2 by April 2023
ECDS update and future
ECDS v4 in the future, UG warned PS of ECDS schema exhaustion
42 providers submitting CDS 6.2.3 to SUS+
SUS+ Service Update
interchange surge at 4pm on inclusion day caused PbR extract start of processing delay
new records for interchanges and records processed in a month
SUS+ is no longer trimming organisation codes due to ANANA requirement, please do not pad org codes with 00 at the end
SUS+ Product Update
AHAS replacement for HES, development ongoing
DB14 issue of 3 discs being pulled on inactive site
inactive site power interruption and investigation, this and above caused a delay to replication to cloud
AOB

## 21.07.2021
Casemix - CDS DQ
dropping of diag 01 from some provider submissions
affected providers seem to be using the same XML middleware supplier
Faster SUS+ program
lack of joined up working by NHS England around CDS, frequency and future
CDS6.3 update
ISN published 15/06/2021
XML schema expected to be published September 2021
CDS6.3 go-live April 2022
Expect everyone to be off CDS6.2 by April 2023
SUS+ Service Update
HSSI 22/06/2021 due to deployment to active site in business hours
new rejection for ANANA format (5) in gp practice field (6)
SUS+ Product Update
incident with data on LIVE B but not on LIVE A due to deployment on both sites being too close together on 06/07/2021, all resolved by 14/07/2021 but daily deltas were suspended to protect those data feeds
AOB

## 18.08.2021
Casemix - CDS DQ
data seems to indicate the relaxing of PbR submission deadlines is having an effect on CDS DQ
issues identified with duplicate submissions of records due to mixing cds sender ids
Faster SUS+ program
80% of all providers now submit weekly APC and OP to SUS+
CDS6.3 update
XML schema expected to be published September 2021
CDS6.3 go-live April 2022
Expect everyone to be off CDS6.2 by April 2023
SUS+ Service Update
average number of interchanges processed per day, July 2020 - 260, July 2021 - 300
DQ Dashboards are not part of SUS+, all issues need to be aised via email to enquiries@nhsdigital.nhs.uk
SUS+ Product Update
incident with data on LIVE B but not on LIVE A due to deployment on both sites being rebuilt too close together on 06/07/2021, all resolved by 14/07/2021 but daily deltas were suspended to protect those data feeds
working with PHIN to enable submission of NHS and private activity to SUS+ and stop the parrallel submision to PHIN
AOB

## 15.09.2021
Casemix - CDS DQ
issue with one site submitting CTV codes
analysis passed to SUS+ and NCDR team
Faster SUS+ program
no update given
CDS6.3 update
CDS6.3 go-live April 2022
Expectation is everyone to be off CDS6.2 by April 2023
recording BMI in CDS submissions, quicker way is an expansion of obesity ICD-10 codes
SUS+ Service Update
push to move NCDR extracts off the SUS+ portal
SUS+ Product Update
PbR 21/22 final tariff due in SUS+ soon
cloud migration - replication to cloud Sept/Oct, dual running Nov and Dec, switch over Jan 2022
AOB

## 20.10.2021
CDS6.3 update
CDS6.3 go-live April 2022
Expectation is everyone to be off CDS6.2 by April 2023
confusion around the use of discharge ready date
Faster SUS+ program
ask of providers to submit cds 180, 190 and 200 to SUS+ weekly
ECDS implementation feeback
ECDS futures
ECDS v4 expected April 2023
a lot of work to be done for SDEC
SUS+ Service Update
all SLAs hit and system was stable
rebalance of nodes on LIVE B gained 9% disk space to bring total disk space down to 80%, enough to get SUS+ to the Cloud
SUS+ Product Update
PbR 21/22 final tariff due in SUS+ soon
cloud migration - replication to cloud during October, dual running Nov and Dec, switch over Jan 2022
AOB
Casemix DQ - please see DQ Dashboard web page
https://digital.nhs.uk/services/secondary-uses-service-sus/sus-data-quality-reporting
This is not part of the SUS+ service

## 24.11.2021
CDS6.3 update
CDS6.3 go-live April 2022
Expectation is everyone to be off CDS6.2 by April 2023
updated schema due any day
Faster SUS+ program
ask of providers to submit cds 180, 190 and 200 to SUS+ weekly
SUS+ Service Update
all SLAs hit and system was stable
SUS+ Product Update
cloud migration - replication to cloud during October, dual running Nov and Dec, switch over Jan 2022
21/22 final PbR tariff applied to SUS+ 10/11/2021
ECDS SNOMED approved and mapped code lists to be applied to SUS+ 24/11/2021
AOB

## 15.12.2021
CDS6.3 update
CDS6.3 go-live April 2022
Expectation is everyone to be off CDS6.2 by April 2023
updated schema now published
DSAS web page correction for weekly APC and OP flow for CDS6.2, CDS6.2.0 and CDS6.3
Faster SUS+ program
ask of providers to submit cds 180, 190 and 200 to SUS+ weekly
Casemix DQ analysis
https://digital.nhs.uk/services/secondary-uses-service-sus/sus-data-quality-reporting
SUS+ Service Update
all SLAs hit and system was stable
Readmissions extract final run January 2022
SUS+ Product Update
cloud migration - replication complete, dual running December and Janaury inclusions, cut over end February 2022
AOB
Net submission considerations
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-services-sus-guidance
Submitting CDS Data To SUS
page 13

## 19.01.2022
CDS6.3 update
CDS6.3 go-live April 2022
Expectation is everyone to be off CDS6.2 by April 2023
updated schema now published
issue with covid ward (virtual) at home guidance and not being part of cds submission
Faster SUS+ program
ask of providers to submit cds 180, 190 and 200 to SUS+ weekly
ECDS update
lack of guidance but deadline remains for conformance is very concerning to users
ECDS v4 April 2023, conflicts with CDS6.3
SUS+ Service Update
all SLAs hit and system was stable
SUS+ Product Update
cloud migration - replication complete, dual running December and Janaury inclusions, cut over end February 2022
Casemix update
Consultation grouper published
AOB

## 16.02.2022
CDS6.3 update
CDS6.3 go-live April 2022
flow of SNOMED codes need to be controlled or not allowed
Faster SUS+ program
ask of providers to submit cds 180, 190 and 200 to SUS+ weekly
ECDS update
ECDS v4 starting April 2023
SUS+ NCDR daily delta extract schedule time moved to 05:10, data as at 05:00.
SUS+ Service Update
all SLAs hit and system was stable
increase in wait for inclusion extracts due to system workload and YTD DSCRO extracts
SUS+ Product Update
cloud migration - replication complete, dual running December and February inclusions
migration date now possibly April 2022
single supplier still not started on SUS+
CDS6.3 deelopment close to completion
AOB
Virtual wards lack of guidance is now causing providers serious issues

## 16.03.2022
CDS6.3 update
CDS6.3 go-live April 2022
flow of SNOMED codes need to be controlled or not allowed
Faster SUS+ program
ask of providers to submit cds 180, 190 and 200 to SUS+ weekly
ask of providers to not wipe weekly submitted data at inclusion
ECDS update
ECDS v4 starting April 2023
SUS+ NCDR daily delta extract schedule time moved to 05:10, data as at 05:00.
SUS+ Service Update
all SLAs hit and system was stable
sev 2 PHIN issue
SUS+ Product Update
cloud migration - replication complete, dual running December and February inclusions
migration date now May 2022
single supplier still not started on SUS+
CDS6.3 development close to completion
AOB

## 20.04.2022
CDS6.3 update
CDS6.3.0 now on TRUD
flow of SNOMED codes need to be controlled or not allowed
Faster SUS+ program
ask of providers to submit cds 180, 190 and 200 to SUS+ weekly
unfinished episode cds types are not mandatory submissions
Provider and site code submissions
providers who sub-contract to private providers need to submit valid site codes in ODS
ECDS update
ECDS v4 starting April 2023
CDS6.2.1 to be removed from SUS+ by June 2022
SUS+ Service Update
all SLAs hit and system was stable
rejections increased due to padding 00 at end of provider code
SUS+ Product Update
cloud migration - replication complete, dual running December and February inclusions
migration date now July 2022
single supplier being onboarded to SUS+
AOB

## 18.05.2022
CDS6.3 update
CDS6.3.0 now on TRUD
do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
U groupings
Barts duplicate episodes have created an increase in U groupings
Casemix DQ Dashboard demo
ECDS update
ECDS v4 starting April 2023
CDS6.2.1 to be removed from SUS+ by June 2022
SDEC and virtual wards guidance required
SUS+ Service Update
all SLAs hit and system was stable
SUS+ Product Update
cloud migration - replication complete, dual running December and February inclusions
migration date now August 2022
single supplier being onboarded to SUS+, issue with security clearance of engineers
AOB

## 15.06.2022
CDS6.3 update
CDS6.3.0 schema is being removed from SUS+ and TRUD
CDS6.3.1 schema to be released soon
do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
SUS+ Service Update
record number of interchanges processed in one day on 18/05/2022
all SLAs hit and system was stable
SUS+ Product Update
cloud migration - replication complete, dual running December and February inclusions
migration date now August 2022
single supplier being onboarded to SUS+, issue with security clearance of engineers
single supplier moved to support SUS+ with IW back up
AOB
ECDS SNOMED mapped list to not change in near future, still provides mapping of snomed to A&E treatment and investigation codes

## 20.07.2022
CDS6.3 update
CDS6.3.1 schema to be in SUS+ by 10pm on 27/07/2022
do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
SUS+ and XML middleware suppliers will be dual running CDS6.2 and CDS6.3.1 from July 2022 onwards
SUS+ Service Update
all SLAs hit and system was stable
SUS+ Product Update
migration date now August 2022
single supplier being onboarded to SUS+, issue with security clearance of engineers
single supplier moved to support SUS+ with IW back up
Faster SUS+
ask for all providers to submit 5 weeks rolling update to SUS+ for OP, APC and unfinished episodes weekly
some providers have issues of submitting weekly updates in July 2022 that run into June 2022 data
AOB

## 17.08.2022
CDS6.3 update
CDS6.3.1 schema in SUS+ and one private sector provider has submitted
do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
SUS+ will not force submitters to move to CDS6.3.1 and not allow them to move back to CDS6.2 or CDS6.2.0
SUS+ Service Update
all SLAs hit and system was stable
SUS+ Product Update
migration date now 02/09/2022
SUS single supplier assessment during September and on point for all activities for October 2022
IW people to be in shadow to Cognizant from October 2022 and running AWS infrastructure
SUS+ experienced developers are being retained as a fall back position
Faster SUS+
ask for all providers to submit 5 weeks rolling update to SUS+ for OP, APC and unfinished episodes weekly
some providers have issues of submitting weekly updates in July 2022 that run into June 2022 data
AOB
proposal to limit BULK interchange cds report period to 365 days
proposal to limit the date range of SUS+ portal extracts to 365 days
ther is no push from NHS Digital to have submitters use NET protocol

## 21.09.2022
CDS6.3 update
do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
SUS+ will not force submitters to move to CDS6.3.1 and not allow them to move back to CDS6.2 or CDS6.2.0
Discharge Ready Date revised definition and examples
SUS+ Service Update
all SLAs hit and system was stable
SUS+ Product Update
migrated to cloud on 03/09/2022
IF-DLP unavailable 5th and 6th September
RIAK 2i query (DSCROs) performance issue still being investigated
IW people to be in shadow to Cognizant from October 2022 and running AWS infrastructure
Faster SUS+
ask for all providers to submit 5 weeks rolling update to SUS+ for OP, APC and unfinished episodes weekly
AOB
Issue with System C implementing the CDS6.3.1 schema on a 1 to 1 basis and no longer having the data item sex in the PAS

## 19.10.2022
CDS6.3 update
do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
SUS+ will not force submitters to move to CDS6.3.1 and not allow them to move back to CDS6.2 or CDS6.2.0
SUS+ Service Update
all SLAs hit and system was stable
RIAK 2i performance issue
July 2022 PbR PREC extracts missing data
SUS+ Product Update
RIAK 2i query (DSCROs) performance resolved by RIAK upgrade on 10/10/2022
IW people to be in shadow to Cognizant from October 2022 and running AWS infrastructure
Faster SUS+
programme closing down soon
AOB

## 16.11.2022
CDS6.3 update
Do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
What's New message: SUS+ will not remove CDS6.2 or CDS6.2.0 schemas in April 2023
PAS supplier only outputting XML and not CSV is not helpful to trusts
ECDSv4 ISN publication now December 2022
SUS+ Service Update
All SLAs hit and system was stable
New record of total monthly interchanges processed
SUS+ Product Update
3rd 2022/23 PbR tariff due 30/11/2022
Working to get 22/23 logs off tin and into Cloud by 02/12/2022
Faster SUS+
95% of providers are submitting APC weekly
Faster Data Flows programme
AOB
Patient opt outs in CDS6.3 submission guidance

## 21.12.2022
CDS6.3 update
Do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
5 providers submitting CDS6.3.1 interchanges
Only 2 XML middleware suppliers assured on CDS6.3 (SystemC and IUVO)
CDS v6.3 User Guidance likely to be updated soon (covering personalised follow up and multiple commissioners)
NHS E funding for CDS6.3 in 22/23 does not exist. Outstanding actions around user guidance (6.2 to 6.3 and patient opt outs)
SUS+ Service Update
All SLAs hit and system was stable
New record of total monthly interchanges processed
Issue with a provider sending mass duplicated cds unique ids in a bulk interchange
SUS+ Product Update
3rd 2022/23 PbR tariff made live in SUS+ on 15/12/2022
19/20 data to be made available again on SUS+ portal for 05/01/2023
Decommissioning of SUS+ tin in January 2023
RIAK upgrade to 3.0.12 in January 2023
CDS6.3 data items replacing CDS6.2 data items
AOB

## 18.01.2023
CDS6.3 update
Do not submit SNOMED codes as SUS+ will not process them without an updated Legally Restricted list
5 providers submitting CDS6.3.1 interchanges, Dedalus are not an XML middleware supplier
Only 2 XML middleware suppliers assured on CDS6.3 (SystemC and IUVO)
CDS v6.3 User Guidance likely to be updated soon (covering personalised follow up and multiple commissioners)
NHS E funding for CDS6.3 in 22/23 does not exist. Outstanding actions around user guidance (6.2 to 6.3 and patient opt outs)
Faster Data Flows
30 data item submissions for admitted, discharged, and OP
data is only last 24 hours
burden reduction is questionable with faster SUS ask still active
SUS+ Service Update
All SLAs hit and system was stable
New record of total monthly interchanges processed
Issue with a provider sending mass duplicated cds unique ids in a bulk interchange
SUS+ Product Update
3rd 2022/23 PbR tariff made live in SUS+ on 15/12/2022
19/20 data to be made available again on SUS+ portal for 05/01/2023
Decommissioning of SUS+ tin in January 2023
RIAK upgrade to 3.0.12 in January 2023
ECDSv4 and SDEC
ECDSv4 ISN published, live in SUS+ 01/07/2023
type 5 and 6 guidance required
AOB
virtual wards via CDS is not a good idea as current guidance clearly states not to submit this in CDS
best solution for virtual wards is a new CDS type

## 15.02.2023
Faster Data Flows
30 data item submissions for admitted, discharged, and OP
data is only last 24 hours
burden reduction is questionable with faster SUS ask still active
SUS+ Service Update
All SLAs hit and system was stable
New record of total monthly interchanges processed and records
SUS+ Product Update
ECDSv2 will be removed from SUS+ on 01/03/2023
23/24 tariff due in March 2023
ECDSv4 and SDEC
ECDSv4 ISN published, live in SUS+ 01/07/2023
type 5 and 6 guidance required
AOB

## 15.03.2023
Faster Data Flows
all questions need to be sent to the FDF forum
england.fdf@nhs.net
SUS+ Service Update
All SLAs hit and system was stable
SUS+ Product Update
ECDSv2 will be removed from SUS+ on 01/03/2023
23/24 consultation tariff due in March 2023
ECDSv4 and SDEC
ECDSv4 ISN re-published
type 5 and 6 guidance required
AOB

## 19.04.2023
Discharge Ready Date
SUS+ Service Update
All SLAs hit and system was stable
SUS+ Product Update
SoW approval for 6 months
ECDSv4 and SDEC
ECDSv4 ISN re-published
type 5 and 6 guidance required
AOB

## 17.05.2023
ECDSv4 and SDEC
ECDSv4 ISN re-published
type 5 and 6 guidance required
SUS+ Service Update
All SLAs hit and system was stable
New record number of records processed in April 2023 (190 million)
SUS+ Product Update
SoW approval for 6 months
AOB
Discharge Ready Date

## 21.06.2023
CDS6.3 update
new schema required (CDS6.3.2 ?)
ECDSv4 and SDEC
ECDSv4 01/07/2023
SUS+ Product Update
SoW approval for 6 months
SUS+ Service Update
All SLAs hit and system was stable
New records set for number of interchanges and number of records processed in May 2023
AOB

## 19.07.2023
CDS6.3 update
new schema required (CDS6.3.2 ?)
ECDSv4 and SDEC
ECDSv4 01/07/2023
SUS+ Product Update
SoW approval for 6 months
work to make SUS+ portal and DLP work with NHS Credential manager
SUS+ Service Update
All SLAs hit and system was stable
AOB
Concerns around support of CDS6.2.0 and CDS6.3.1 schemas by EMIS
System C withdrawing from the XML middlware supplier market

## 16.08.2023
CDS6.3 update
new schema required (CDS6.3.2 ?)
CDS DQ update
https://prezi.com/view/lGma2PSYInyB2iCsLn1R/
SUS+ Product Update
SoW approval for 6 months
work to make SUS+ portal and DLP work with NHS Credential manager
SUS+ Service Update
All SLAs hit and system was stable
AOB
Possible change to PbR processing logic for discharge ready date

## 20.09.2023
ECDSv4 update
first v4 submitter in September 2023
ECDS max due October 2023
CDS DQ update
CDS data is the best quality acute data NHS England have access to
DQ issues with April 2023 data for a handful of providers
SUS+ Product Update
CIS migration of IF_DLP from v1 to v2 going ahead
Python upgrade to v3.10
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 18.10.2023
ECDSv4 update
first v4 submitter in September 2023
ECDS max due November 2023
CDS DQ update
Unfinished episodes automated weekly submission guidance needed
SUS+ Product Update
CIS migration of IF_DLP from v1 to v2 going ahead
Python upgrade to v3.10
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 15.11.2023
ECDSv4 update
ECDS max due end November 2023
CDS DQ update
data is invaluable and the coding is needed for analysis
CDS DQ Dashboards
survey still open
dashboards are widely used and very useful
SUS+ Product Update
CIS migration of IF-DLP from v1 to v2 going ahead
Python upgrade to v3.10
SUS+ Service Update
All SLAs hit and system was stable
AOB
24/25 SUS+ Submission timetable DRAFT

## 20.12.2023
ECDSv4 update
ECDS max due end November 2023
LoS Community beds
proposal is to have community beds marked in ward code CDS data item
further engagement required
CDS DQ Dashboards
survey completed
dashboards are widely used and very useful
SUS+ Product Update
CIS migration of IF-DLP from v1 to v2 going ahead
Python upgrade to v3.10
DLP submission meta data to only 3 months
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 17.01.2024
ECDSv4 update
EMED3 FIT NOTE ISSUER
ECDS Diagnosis Max live in SUS+
CDS analysis
upcoming workshop for Faster SUS program benefits and fit for purpose
CDS data invaluable for analysis on a weekly basis
SUS+ Product Update
CIS migration of IF-DLP from v1 to v2 going ahead
CDS6.3 data items in portal extracts, spec to come
DLP submission meta data to only 3 months
SUS+ Service Update
All SLAs hit and system was stable
SUS+ lost 3 hours processing time on inclusion due to provider NET interchange issue
AOB

## 21.02.2024
ECDSv4 update
EMED3 FIT NOTE ISSUER required data item from 01/04/2024
ECDS Diagnosis Max update for SUS+ from 01/04/2024
CDS analysis
paper to detail the wider value of clinical coding in CDS/SUS from a secondary use/ NHSE perspective being worked on
no update regarding submission frequency
SUS+ Product Update
CIS migration of IF-DLP from v1 to v2 going ahead but removal of IF-DLP now after April 2024
CAM logic change for 24/25
SUS+ Service Update
All SLAs hit and system was stable
Portal extract issue with 4 extracts returning zero records
AOB
SUS+ UG 24/25 calendar invites to be sent out in March 2024
Proposal to limit BULK interchange to 365 days
Proposal to limit portal extracts to 365 days

## 20.03.2024
ECDSv4 update
EMED3 FIT NOTE ISSUER required data item from 01/04/2024
ECDS Diagnosis Max update for SUS+ from 01/04/2024
CDS analysis
paper to detail the wider value of clinical coding in CDS/SUS from a secondary use/ NHSE perspective being worked on
reminder to submit unfinished episodes to SUS+
possible issue of type 04 walkin centre activity not able to submit through ECDSv4
SUS+ Product Update
CIS migration of IF-DLP from v1 to v2 going ahead but removal of IF-DLP now September 2024
CAM logic change for 24/25
NHS Credential manager for DLP end April 2024 and SUS+ end May 2024.
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 18.04.24
CDS analysis
paper to detail the wider value of clinical coding in CDS/SUS from a secondary use/ NHSE perspective being worked on
reminder to submit unfinished episodes to SUS+
possible issue of type 04 walkin centre activity not able to submit through ECDSv4
SUS+ Product Update
CIS migration of IF-DLP from v1 to v2 going ahead but removal of IF-DLP now September 2024
CAM logic change for 24/25
NHS Credential manager for DLP end April 2024 and SUS+ end May 2024.
SUS+ Service Update
All SLAs hit and system was stable
expected schema removal dates for SUS+ are now….
|  | CDS6.2 | 2025-04-01
|  | ECDSv3 | 2025-04-01
AOB

## 15.05.24
CDS analysis
paper to detail the wider value of clinical coding in CDS/SUS from a secondary use/ NHSE perspective being worked on
possible issue of type 04 walkin centre activity not able to submit through ECDSv4
SUS+ Product Update
CIS migration of IF-DLP from v1 to v2 going ahead but removal of IF-DLP now September 2024
CAM logic change for 24/25
NHS Credential manager for DLP end May 2024 and SUS+ end May/early June 2024.
SUS+ Service Update
All SLAs hit and system was stable
expected schema removal dates for SUS+ are now….
|  | CDS6.2 | 2025-04-01
|  | ECDSv3 | 2025-04-01
AOB
please submit for annual refresh this week, Monday will be mental.
On Monday we expect extracts for 23/24 and 24/25.
Business hours are 8am to 6pm Monday to Friday, if you submit on the weekend we will only action on Monday.
Make sure your contact details are up to date, email me if you want to check them.

## 19.06.24
CDS DQ Dashboards
moving under Tom Mason's NHS E analysis area
user engagement asked for by UG members when CDS DQ Dashboards are updated
SUS+ Product Update
DLP now using NHS Credential manager, IF-DLP removal extended to September 2024
CAM logic change for 24/25 to be published
SUS+ to use NHS Credential manager from 26/06/2024
ECDS comms about v3 out soon
SUS+ Service Update
All SLAs hit and system was stable
New records set for number of records processed in a month, interchanges in a month and interchanges in a day.
AOB

## 17.07.24
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis
pathways as new means to assess productivity in the NHS
SUS+ Product Update
SUS+ to use NHS Credential manager from 26/06/2024
DLP now using NHS Credential manager, IF-DLP removal extended to September 2024
CAM logic change for 24/25 to be published
ECDSv4 data items in portal extracts this summer
SUS+ Service Update
All SLAs hit and system was stable
New record set for number of records processed in a month due to the increase in test interchanges sent.
AOB
Inablity to submit type 4 WIC activity in ECDSv4

## 18.09.24
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis
SNOMED CDS6.3 data items not being processed due to the legally restricted list not having SNOMED codes.
Opt in SNOMED code list can be created for certain CDS6.3 data items
HRG DQ is down for 24/25
SUS+ Product Update
OKTA replacement for IF-DLP 30/09/2024
remove 19/20, 20/21, 21/22 data from SUS+ portal to move back to current year plus 2
CDS6.3 gender X being mapped to 0, fix to be done soon.
SUS+ Service Update
All SLAs hit and system was stable
AOB
Tuesday 17/09/2024 940 interchanges and 23 million records submitted to SUS+ (new records), please don't submit a mid year refresh in inclusion week.

## 16.10.24
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis
HRG DQ is down for 24/25
Lack of clinical coders is causing a coding backlog
SUS+ Product Update
remove 19/20, 20/21, 21/22 data from SUS+ portal to move back to current year plus 2
ECDSv4 data items in portal extracts soon
24/25 updated tariff deployed to SUS+
SUS+ Service Update
All SLAs hit and system was stable
Tuesday 17/09/2024 940 interchanges and 23 million records submitted to SUS+ (new records), please don't submit a mid year refresh in inclusion week.
AOB

## 20.11.24
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis
HRG DQ is down for 24/25
Lack of clinical coders is causing a coding backlog
SUS+ Product Update
remove 19/20, 20/21, 21/22 data from SUS+ portal to move back to current year plus 2
ECDSv4 data items in portal extracts soon
SUS+ Service Update
All SLAs hit and system was stable
Impact of ERF YTD submission on SUS+ processing
AOB

## 18.12.24
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
HRG DQ is down for 24/25
Lack of clinical coders is causing a coding backlog
24/25 coding will not be anywhere near complete come May 2025 annual refresh
SUS+ Product Update
remove 19/20, 20/21, 21/22 data from SUS+ portal to move back to current year plus 2
ECDSv4 data items in portal extracts soon
IF-DLP is now gone. DLP access now via CIS2 and NHSE Apps
SUS+ Service Update
All SLAs hit and system was stable
Impact of ERF YTD submission on SUS+ extract processing
AOB

## 15.01.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
HRG DQ is down for 24/25
Lack of clinical coders is causing a coding backlog
24/25 coding will not be anywhere near complete come May 2025 annual refresh
SUS+ Product Update
remove 19/20, 20/21, 21/22 data from SUS+ portal to move back to current year plus 2
ECDSv4 data items in portal extracts soon
25/25 tariff, HRG grouper and PSS grouper are due
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 19.02.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
HRG DQ is down for 24/25
Lack of clinical coders is causing a coding backlog
24/25 coding will not be anywhere near complete come May 2025 annual refresh
SUS+ Product Update
ECDSv4 data items in portal extracts soon
25/26 consultation tariff deployed on 10/02/2025
Best Practice flags to be implemented outside the grouper in SUS+
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 19.03.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
CDS data is very powerful and useful
CDS freeze data DQ
UZ01Z HRGs have increased in some months to 5%
Lack of clinical coders is causing a coding backlog
24/25 coding will not be anywhere near complete come May 2025 annual refresh
SUS+ Product Update
25/26 consultation tariff deployed on 10/02/2025
Best Practice flags to be implemented outside the grouper in SUS+
CAM will be updated in 25/26
Legally Restricted Code list now available
SUS+ Service Update
All SLAs hit and system was stable
sev 1 unplanned outage on 25/02/2025
AOB
SUS+ UG invites for 25/26 to be sent on Monday 24/03/2025

## 23.04.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
CDS data is very powerful and useful
24/25 coding will not be anywhere near complete come May 2025 annual refresh
SUS+ Product Update
25/26 HRG grouper and PSS grouper in SUS+
25/26 Tariff implemented 10/04/2025
Updated reference data made live in SUS+ for ECDS max, approved and mapped code lists 10/04/2025
Right Procedure Right Place derivations implemented 10/04/2025
CAM will be updated in 25/26, by May 2025
Legally Restricted Code list to be in SUS+ asap
SUS+ Service Update
All SLAs hit and system was stable
25/26 average interchanges processed per day 500+ and records processed per day 8 million
AOB

## 21.05.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
CDS data is very powerful and useful
24/25 coding will not be anywhere near complete come May 2025 annual refresh
SUS+ Product Update
Updated reference data made live in SUS+ for ECDS max, approved and mapped code lists 10/04/2025
CAM 25/26 updated in system on 15 May 2025
New Legally Restricted Code list will not be in SUS+, as data moves out of NHS E then legally restricted code list has to be actioned
SUS+ Service Update
All SLAs hit and system was stable
25/26 average interchanges processed per day 500+ and records processed per day 8 million
AOB

## 26.06.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
CDS data is very powerful and useful
Ongoing issue of poor coding of non elective data
SUS+ Product Update
Tech debt actioned on Python, Grafana and Prometheus
GPDC migration off RIAK
New Legally Restricted Code list will not be in SUS+, as data moves out of NHS E then legally restricted code list has to be actioned
SUS+ Service Update
All SLAs hit and system was stable
Records broken for interchanges and records processed in a month and a single day
AOB
Work ongoing around discharge ready date

## 23.07.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
SUS+ Product Update
new developments for tariff and unbundled
DLP migration off RIAK soon
New Legally Restricted Code list will not be in SUS+, as data moves out of NHS E then legally restricted code list has to be actioned
SUS+ Service Update
All SLAs hit and system was stable
AOB
FDP as a data warehouse allows CSV output of CDS to then be converted to XML

## 20.08.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
SUS+ Product Update
new developments for tariff and unbundled
DLP migration off RIAK soon
New Legally Restricted Code list will not be in SUS+, as data moves out of NHS E then legally restricted code list has to be actioned
June pay award update in SUS+ 28/8/2025
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 24.09.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
CDS data is very powerful and useful
ongoing issue with poor DQ in non-elective data
Paper to Jim Mackey to demand SDEC remains in APC and is not moved to ECDS
SUS+ Product Update
DLP migration from RIAK to DynamoDB completed
New Legally Restricted Code list will not be in SUS+, as data moves out of NHS E then legally restricted code list has to be actioned
SUS+ portal to only allow data from April 2023 onwards (2 years plus current)
SUS+ Service Update
All SLAs hit and system was stable
AOB
ICBs seeing nulled cds unique ids (which is a non PCD field) when PCD data like Hopsital Provider Spell Number is submitted
potential guidance coming to demand discharge ready date is completed for patients in hospital for a minimum amount of time

## 22.10.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
comparison of HODF data and SUS+ data
ongoing issue with poor DQ in non-elective data
ability to flow SNOMED controlled codes in SUS+ being explored
SUS+ Product Update
DLP migration from RIAK to DynamoDB completed
Python migration moving ahead as planned
Legally Restricted Code list will not be in NHS England stystems, action taken
SUS+ Service Update
All SLAs hit and system was stable
AOB
no consultation grouper will be made available this year
SDEC could remain in APC data flow, action taken

## 19.11.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
SDEC to ECDS pause letter coming
ongoing issue with poor DQ in non-elective data
ability to flow SNOMED controlled codes in SUS+ being explored
SUS+ Product Update
Consultation prices for December 2025
Python migration moving ahead as planned
Awaiting Legally restricted code list removal edict
SUS+ Service Update
All SLAs hit and system was stable
Issue with PbR scheduled extracts not loading from portal
AOB
26/27 SUS+ Submission timetable draft proposal with same deadlines as last year

## 17.12.25
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
SDEC to ECDS pause communications done
Potential to change an admission method code for SDEC in APC
ongoing issue with poor DQ in non-elective data
SUS+ Product Update
Consultation prices for December 2025
Python migration moving ahead as planned
Awaiting Legally restricted code list removal edict
Migration from RIAK to Dynamo DB for March 2026
ECDSv4 data items in extracts early 2026
SUS+ Service Update
All SLAs hit and system was stable
AOB
Guidance proposed to limit daily submission of interchanges to cover min 7 and max 30 days
Guidance proposed to limit weekly submission of interchanges to cover min 14 and max 60 days
Question asked about the impact of purging inactive records mid year (January) as well as July for a completed financial year

## 21.01.26
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
CDS analysis and coding
SDEC in ECDS and APC, workshops to take place next week
Coding lag of at least 4 months seen
ongoing issue with poor DQ in non-elective data
SUS+ Product Update
Python migration to v3 completed
Awaiting Legally restricted code list removal edict
Migration from RIAK to Dynamo DB for March 2026
ECDSv4 data items in extracts January 28th release
SUS+ Service Update
All SLAs hit and system was stable
AOB
Purging inactive records paper sent for feedback

## 18.02.26
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
SDEC workshop
SDEC in ECDS is now EEMAC
Specialty SDEC to flow in APC CDS, with ward code flag proposed
Follow up workshops required
SUS+ Product Update
Awaiting Legally restricted code list removal edict
Migration from RIAK to Dynamo DB for March 2026
ECDSv4 data items in extracts 5th February 2026
Issue with 25/26 CAM resolved by release on 5th February
Issue with non consultant prices to be resolved by release on 25th February
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 18.03.26
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
SDEC workshop
SDEC in ECDS is now EEMAC
Specialty SDEC to flow in APC CDS, with ward code flag proposed
Follow up workshops required
Guidance due end April 2026
SUS+ Product Update
Awaiting Legally restricted code list removal edict
Migration from RIAK to Dynamo DB for April 2026
No 26/27 HRG grouper or PSS grouper
Bridging file needed for OPCS4.11 to 4.10
SUS+ Service Update
All SLAs hit and system was stable
AOB

## 29.04.26
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
SDEC workshop
SDEC in ECDS is now EEMAC
Specialty SDEC to flow in APC CDS, with ward code flag proposed
Follow up workshops required
Guidance due May 2026
SUS+ Product Update
Awaiting Legally restricted code list removal edict
Migration from RIAK to Dynamo DB for early May 2026
No 26/27 HRG grouper or PSS grouper
Bridging file published for OPCS4.11 to 4.10
SUS+ Service Update
All SLAs hit and system was stable
| AOB | 25/26 annual refresh
https://digital.nhs.uk/services/secondary-uses-service-sus/submitting-cds-data-to-sus/missed-inclusion-dates-and-retrospective-submissions
Contact HES via email to hes.questions@nhs.net and they will make a decision to apply a daily delta from SUS+ at a later date.

## 20.05.26
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
SDEC workshop
SDEC in ECDS is now EEMAC
Specialty SDEC to flow in APC CDS, with ward code flag proposed
Follow up workshops required
Guidance due June 2026
SUS+ Product Update
Awaiting Legally restricted code list removal edict
Migration from RIAK to Dynamo DB for end of May 2026
No 26/27 HRG grouper or PSS grouper
Bridging file for OPCS4.11 to 4.10, incorporated into 25/26 auto grouper
MSDS vs CDS
Ask for users to engage with Ceri Townley
SUS+ Service Update
All SLAs hit and system was stable
| AOB | 25/26 annual refresh
https://digital.nhs.uk/services/secondary-uses-service-sus/submitting-cds-data-to-sus/missed-inclusion-dates-and-retrospective-submissions
Contact HES via email to hes.questions@nhs.net and they will make a decision to apply a daily delta from SUS+ at a later date.

## 17.06.26
https://digital.nhs.uk/services/secondary-uses-service-sus/secondary-uses-service-sus-user-group
SDEC and EEMAC
SDEC in ECDS is now EEMAC, SDEC is now speciality SDEC for APC
Specialty SDEC to flow in APC CDS, with ward code flag proposed
Guidance due July 2026
SUS+ Product Update
Awaiting Legally restricted code list removal edict
Migration from RIAK to Dynamo DB for end of August 2026
No 26/27 HRG grouper or PSS grouper
Bridging file for OPCS4.11 to 4.10, incorporated into 25/26 auto grouper
MSDS vs CDS
Ask for users to engage with Ceri Townley
SUS+ Service Update
All SLAs hit and system was stable
new records set for total interchanges processed in a month, in a day and records in a day.
AOB

## Open Actions
SUS+ User Group Action Log Updates since last SUS+ User Group are in bold
Action No. | Date raised | Action | Owner | Status | Action Update | Position | Start
63 | 15.12.2021 | CDS6.3.1 schema progress of onboarding submitters | JS/TL | Open | 17.06.2026 No update 21.02.2024 EMIS decmac approved for CDS6.3.1. Comms isued to confirm removal of CDS6.2 will not be April 2024. 17.01.2024 No update 15.11.2023 EMIS still not assured. 18.10.2023: EMIS started assurance in July 2023, last contact to finalise Devmac was 06/09/2023. 20.09.2023 IUVO, IQVIA, System C assured. | 61% on CDS6.3.1 39% on CDS6.2 (6.2.0) | July 2022 (3 years+)
69 | 15.11.2023 | ECDSv4 XML middleware supplier assurance | JS/JE | Open | 17.06.2026 EMIS re-engaged with testing team for assurance 19.11.2025 No update 15.11.2023: NEW, Only IUVO assured. | 57% on ECDSv4 43% on ECDSv3 | July 2023 (2 years+)
73 | 22.10.2025 | Official comms for the discussion to allow SDEC to remain in APC data flow | TM/JE | Open | 17.06.2026 No update 22.10.2025 New action | comms published on SUS+ What's New on 10/02/2025
74 | 22.10.2025 | Legally restricted code list removal from all NHS England systems | TM/SR | Open | 17.06.2026 No update 22.10.2025 New action | awaiting publication

## Closed Actions
SUS+ User Group Action Log Updates since last SUS+ User Group are in bold
Action No. | Date raised | Action | Owner | Status | Action Update | Closed at last SUS+ UG or Opened
2 | 2019-06-19 | JS to speak to Paul Croft about PHIN. | JS | CLOSED | 18.12.2019: CLOSED 20.11.2019: PHIN is in CDS 6.3, to be deployed in April 2021. JS asked the group if it is acceptable to have the PHIN update within the CDS6.3 update? PHIN is aware of the cds6.2 plan. The Group agreed to the plan. 16.10.2019 JS gave an update: contacted Paul Croft and PHIN are working to get the development proposal, once ready, it will be presented at the User Group. 18.09.2019: Carried over. 21.08.2019: Paul Croft will give another presentation in the coming months and a number of other speakers will attend. 17.07.2019: GH’s details have been passed onto Paul Croft (PC). 19.06.2019: JS has had a conversation with Paul Croft regarding PHIN submitting more data to SUS. On hold. PC to be in touch with Gary and Richard once PHIN is fully up and running. | CLOSED
19 | 2019-07-17 | User Group meeting notes to be written and shared with the group within one week to allow review and follow up on action points | DDC BusOps Team | CLOSED | 18.12.2019. The group has made a decision to utilise an action log that will be circulated within a week from the meeting. 20.11.2019: Ongoing 16.10.2019: KJ to email minutes to SH and JS 18.09.2019: Ongoing. Any areas of uncertainty to be checked prior to publishing. 21.08.2019: PS explained that due to current staffing issues and internal reorganisation no promises can be made as to when the notes are turned around, however the DDC Business Ops Team will continue to do their best. 17.07.2019: The last notes were received a week prior to the meeting, still not there yet as the DDC Business Ops Team are short on resource and are doing their best. | CLOSED
27 | 2019-09-18 | SF to raise the age-related risk on CRIS. | SF | CLOSED | 18.12.2019: Carried over. SF cannot find sufficient reason for raising a risk. Engineers identified £20k of error records with miscalculated PSS over the whole year in NHS so far. If we identify a bigger error then SF will raise a risk. 20.11.2019: Carried over. Chase SF 16.10.2019: Carried over. | ON HOLD?
28 | 2019-09-18 | EnDA survey to be re-issued to the SUS UG. | JS/KJ | CLOSED | 18.12.2019: Closed 20.11.2019: Carried over. JS/KJ to chase. 16.10.2019: Carried over. JS to chase up | CLOSED
31 | 2019-09-18 | ACTION: A SUS+ engineer to attend next month to explain to the group how SUS works with the grouper. | SF | CLOSED | 18.12.2019: SF: JK did a presentation last month. SH wants engineer to come down, to show the diagrams. JSp would like to know why the new in-house Grouper would be faster, as presented by JK in last month's meeting. JSp would like to know the action plan for the in-house Grouper as Casemix needs to prepare and plan for the next year. SF, if the new Grouper will affect the next year planning, then NHSD won't release the Grouper next year. SF was not aware about the time boundry of 3 years with Woodward Associate's contract. SF needs to speak to Roger. In-house Grouper is on hold at the moment. We won't introduce the new Grouper if it is not going to benefit all involved. 20.11.2019: JK to share a presentation 16.10.2019: Carried over. Awaiting documentation. | CLOSED
32 | 2019-10-16 | SF to share EBI Algorithm with the user group | SF | CLOSED | 18.12.2019: PDR Documentation has this information. | CLOSED
33 | 2019-10-16 | Tom Mason to ask NCDR about the policy of archiving and storing the historic records. | TM | CLOSED | 18.12.2019: Closed. 20.11.2019: Tom Mason gave an update. NCDR only retains the current view, updated monthly. There is no archive because of the size. | CLOSED
37 | 2019-11-20 | JK to find out if SF can do show and tell session. | JK | CLOSED | 18.12.2019: Closed | CLOSED
39 | 2019-11-20 | SF to find out why the unified extract by MESH is crossed out. Is it completed or deferred? SF to explain which items are deferred. What does cross outs in previous and future months mean? Provide a legend for the Product Book. SH would like the update before the next User Group. | SF | CLOSED | 18.12.2019: SF reorganised the Product Book. | CLOSED
40 | 2019-11-20 | JS to send PCD Leakage report to AN (completed). | JS | CLOSED | 18.12.2019: Completed. Close the action. | CLOSED
41 | 2019-11-20 | JK to speak to SF about In-house Grouper. SF to give justification of in-house Grouper. | JK/SF | CLOSED |  | CLOSED
42 | 2019-11-20 | SF to publish the AE Patient Group Code for ECDS. | SF | CLOSED | 18.12.2019: Duplicate action. Remove. | CLOSED
21 | 2019-07-17 | Amend Interchange report to go back to the sender. | SF | CLOSED from last meeting | 19.02.2020: Completed 18.12.2019: This item is still in backlog. Carried over. 20.10.2019: Carried over. Chase SF. 16.10.2019: SF is still working on this; the DQ reports go back based on the provider codes submitted. SF needs to do impact assessment of changing over to be the EDI address being the trigger for the reports, not the provider code. 18.09.2019: Carried over, no update 17.07.2019: SF is looking into this. Ongoing. | Close, in live and toggled off will go into operation on 5 March
22 | 2019-09-18 | Link to new flow chart to be published in the minutes. SF to provide. | SF | CLOSED from last meeting | 19.02.2020: Completed 18.12.2019: SF: It is in the PbR guidance document. SF to provide a link to place in the minutes. 20.11.2019: Carried over 16.10.2019: Carried over, SF to provide. 18.09.2019: To be added online in due course. | https://digital.nhs.uk/services/secondary-uses-service-sus/payment-by-results-guidance
34 | 2019-11-20 | SF to publish the A&E Patient Group Code in ECDS. | SF | CLOSED from last meeting | 19.01.2020: SF published A&E patient group code in actions log 15.01.2020: JS provided an update. The updated code was suppose to be provided in October 2019 but it never happened. There is an ongoing issue with ECDS. JK added that SUS+ Team is looking into it now. SH asked for an update in two weeks. 18.12.2019: SF to check if this information is in PbR documentation.
36 | 2019-11-20 | SF to do impact assessment of changing over to be the EDI address being the trigger for the DQ feedback reports, not the provider code. | SF | CLOSED from last meeting | 19.01.2020: SF completed impact assessment of 20 DQ feedback users of which 11 submit for another provider, all happy to move from provider code trigger to EDI address 15.01.2020: Carried Over. 18.12.2019: SF to share the document with the User Group | Done
35 | 2019-11-20 | SF to do the impact assessment for the issue of the age being used on the grouper for this financial year and for the planning of the next financial year. | SF | CLOSED from last meeting | 19.01.2020: SF completed impact assessment 15.01.2020: SH asked JS to chase SF for an update on this in a weeks time. 18.12.2019: SF to share the document with Casemix. | Done
38 | 2019-11-20 | Tom Mason asked a question if unified extracts are available now. JK to find out and give an update before the next meeting. | JK/SF | CLOSED from last meeting | 19.02.2020: Unified extracts are available in beta, first set delivered to NCDR 15.01.2020: JK provided an update. SUS+ Team is meeting with DSCRO to discuss testing of unified extracts. 18.12.2019: SF gave an update. It will be released in Januray 2020. It is being tested now.
43 | 2019-11-20 | JS to provide an estimate of how much resource it would take to create a report each month. | JS | CLOSED from last meeting | 19.02.2020: TM happy with solution provided by SUS+ Service Owner 15.01.2020: TM has agreed the inclusion plus 3 is okay. TO BE CLOSED 18.12.2019: Cut off date statement has been published yesterday. Other reports are not time or cost efficient i.e. frozen views, current views. Monthly submission report is done on a monthly basis and does not take long to produce. JS to provide a report of which trusts are submitting after the inclusion date. | Done
2020-01-15 | SF to send the date SUS+ requires all PbR ref data to be handed over to Casemix so they know. Timeline of each action. | SF/JK | Open | 19.02.2020: If the ref data arrives on or before the 23/03/2020, SUS+ will be able to deploy the new groupers and tariff by 01.04.2020 | Closed, due to deadline of 01/04/2020 passing | Done
51 | 2020-02-19 | SH to escalate inclusion deadline issues to SUS+ Board | SH | CLOSED | DONE - 13.05.2020 - SUS+ Strategic Steering Group made aware of issues on 13.05.2020 | Done
52 | 2020-05-20 | Publish FHIR consultation link on SUS+ What's New | JS | CLOSED | DONE - 27/05/2020 | Done
53 | 2020-05-20 | Publish uses of CDS data by PHE, Oxford and NHS E | JS | CLOSED | DONE - 28/05/2020 | Done
54 | 2020-06-17 | Publish Oxford uses of SUS+ data | JS | CLOSED | Done 25/06/2020
55 | 2020-06-17 | impact of not trimming provider codes | JS | CLOSED | Done 25/06/2020
45 | 2020-01-15 | Update on MAR QA | TM | CLOSED | 15.07.2020: Done 19.02.2020: Carried over. TM to give an update at March 2020 User Group meeting. | MR now
20 | 2019-07-17 | Invite someone from PDS to present at the User Group. | JS | CLOSED | 19.08.2020: PDS team to attend September 2020 User Group 22.04.2020: Carried Over. 19.02.2020: Carried Over. ECDS SDEC expected at March 2020 SUS+ UG. 15.01.2020:Carried over 18.12.2019. Carried Over. 20.10.2019: Keep open. JS chasing PDS team. 16.10.2019: PDS will present when they are ready, JS has chased it up. 18.09.2019: Ongoing, trying to arrange a date. 17.07.2019: Ongoing. JS has made enquiries about PDS. | invite to September 2020 UG
26 | 2019-09-18 | SF/GS to look into the issue of which age is presented to the grouper. | SF | CLOSED | 19.08.2020: to Close? 22.04.2020: Carried Over 19.02.2020: Carried Over 15.01.2020: Carried Over. 18.12.2019: Simon Robinson had a look at it and he still cannot find the problem. We have fixed the age issue so we are sending the correct age to the Grouper. SF to share the spreadsheet with findings with the group and Casemix. 20.11.2019: Carried over. Chase SF. 16.10.2019: SF gave an update: Simon Robinson has spoken to Casemix. The PSS grouper code is now fixed, no other issue with age on the Grouper. Tim Holdsworth disagreed: Simon Robinson needs to come back to speak to the user group. Julie Speller asked if this has been raised with the Board. SF mentions email was sent. SF invited Simon Robinson to come and give an update. Julie Speller noted: we use age at start but PH uses age at end, which is causing a lot of problems. There is a problem with PSR algorithm due to a data quality. Data quality only comes in with age on end, the age at start is causing an error i.e. when children reach 18 years of age. NEW ACTION: SF to do the impact assessment for this financial year and planning for next financial year. NEW ACTION: Julie Speller to discuss with Simon Robinson offline 18.09.2019: Ongoing. | Thus far no users have raised a query about this processing
1 | 2018-03-21 | UG to look at list and put in ranked order the development they would like, with benefits. Next year SUS will cease to be a programme and will, therefore, cease to have their own money. | SF | CLOSED | 18.11.2020: On hold 22.04.2020: On hold 15.01.2020: On hold. 18.12.2019: On hold. 20.11.2019: On hold. 16.10.2019: On hold 18.09.2019: On hold 21.08.2019: On hold 19.06.2019: On hold. 15.05.2019: On hold. 17.04.2019: This item is on hold. 20.03.2019: SF was not available to provide feedback – to be carried over. 16.01.2019: Before the December meeting, a list of potential developments for next year was sent out, and capable of responses were received, and the responses will be shared for people to review and feedback. 19.12.2018: To be discussed during the meeting. 17.10.2018: This item remains on hold. 19.09.2018: To be discussed during the meeting. 15.08.2018: To be discussed during the meeting. 18.07.2018: To be discussed during the meeting. 20.06.2018: List has been sent, replies received, to be left open as a standing item. 16.05.2018: Discussed in the meeting, further scoring to be done. 18.04.2018: Deferred - User Group to look at the list again and rank in order of benefits. 21.03.2018: Have now had ten responses, but GS has also had separate feedback which he has responded to individually.
48 | 2020-01-15 | SF to review how the delivery slides in the product book are presented. Suggestion is to have a Gantt chart to see the timeline of delivery. | SF | CLOSED | 18.11.2020: Carried over 19.02.2020: Carried over. SF mentioned a full review of all product books to be completed by April 2020.
50 | 2020-02-19 | SF to add field "delayed from" to SUS+ Product Book | SF | CLOSED | 18.11.2020: Carried over 19.02.2020: NEW ACTION
51 | 2020-07-15 | Final 20/21 PbR tariff published? | TM | CLOSED | 18.11.2020: Carried over 15.05.2020: NEW ACTION
46 | 2020-01-15 | Update on the FHIR dataset | ChW | CLOSED | 20.01.2021 Carried over. ChW to give monthly updates. 19.02.2020: Carried over. ChW to give monthly updates. | to be closed
52 | 2021-01-20 | SUS+ to detail which DSCROs are receiving unified extracts | SF | CLOSED | 17.02.2021: COMPLETED | Done
53 | 2021-01-20 | SUS+ to implement 20/21 final tariff in SUS+ by March 2021 Inclusion date | SF | CLOSED | 17.03.2021: COMPLETED | Done
54 | 2021-02-17 | NHS England to detail the uses of unfinished episodes in NCDR | TM | CLOSED | 17.02.2021: NEW | Done
49 | 2020-02-19 | SUS+ to publish PCD leakage algorithm | SF | CLOSED | 17.03.2021: Carried over 19.02.2020: NEW ACTION | link
44 | 2019-11-20 | SH would like a full disclosure and documentation of what happened with ECDS. DSAS to publish implementation review of ECDS, once completed. | ChW | CLOSED | 17.03.2021 ECDS PIR ongoing but deprioritised by COVID-19 work 19.02.2020: ChW to provide update at next month's SUS+ UG 15.01.2020: Carried Over. JS mentioned NHS England ECDS team will attend the SUS+ UG in the future. 18.12.2019: GF gave an update. Post implementation review of ECDS is under review because of the SDEC. It will be published when it is completed. It needs to be timely. Comments from providers was that previous publications were useful. TM: we need to understand the issues. SH: it should be shared with us so we can contribute. GF: we have reviewed definitions and gave recommendations for implementations to different users. It is not defined for release yet, we are asking the trusts to give feedback at the moment, it is not being piloted yet. There will be a consultation period. Release planned for April 2021. Paula Monteith: we do not have a tariff for 2020 yet, and what about the tariff 2021. Impact analysis would be helpful for all providers. GF: we will invite SDEC to come and talk to the SUS+ UG. GF: to feedback from today's meeting. | Move to PS
56 | 2021-04-21 | ECDS team to present to SUS+ UG about lessons learned, multiple schemas and future of ECDS | PS | CLOSED | 19.05.2021: PS invited to June 2021 SUS+ User Group 20.04.2021:NEW
61 | 18.08.2021 | Casemix CDS DQ analysis to be passed to SR | JSp | CLOSED | 15.09.2021: Done
59 | 21.07.2021 | Impact analysis of LIVE A and B not in sync | SR | CLOSED | 18.08.2021: Ongoing 19.05.2021: NEW
58 | 16.06.2021 | ECDS futures - invite Lynda Brazier to speak | JS | CLOSED | 18.08.2021: Confirmed 20.10.2021 SUS+ UG 19.05.2021: NEW | done
57 | 19.05.2021 | Weekly data flows to DSCROs | SR/TM | CLOSED | 20.10.2021: Meeting update 19.05.2021: NEW | close action
62 | 24.11.2021 | SUS+ What's New publication 11/11/2021 - final 21/22 tariff applied to SUS+…...clarity required | SR | CLOSED | 24.11.2021: NEW | sorted
55 | 17.03.2021 | Covid ward at home update | TL/TM | CLOSED | 20.07.2022: NHS England guidance published but requires feedback | remove
64 | 19.01.2022 | Burden reduction of stopping ACM and PLCM once submitting weekly APC and OP to SUS+ | TM | CLOSED | 21.09.2022: Ongoing | closed
65 | 16.02.2022 | NHS England provider engagement solution for all data submissions to the centre | TM | CLOSED | 21.09.2022: Ongoing | closed
66 | 19.01.2022 | NHS England data alliance partnership board feedback and provider representation. | TM | CLOSED | standards approval, not burden reduction | closed
60 | 21.07.2021 | Impact of increased U code groupings | TM/JSp | CLOSED | 15.03.2023: Ongoing | close
67 | 15.02.2023 | SDEC pilot site feedback to be shared with the SUS+ UG | JW/SAF | CLOSED | 15.03.2023: Ongoing | published
68 | 15.02.2023 | Recording SDEC in ECDSv1.4 final | JW/SAF/AL | CLOSED | 16.08.2023: Ongoing | Recording SDEC in ECDS Information June 2023 - FINAL APPROVED - ECDS Forum - FutureNHS Collaboration Platform
70 | 15.11.2023 | Share a paper to detail the wider value of clinical coding in CDS/SUS from a secondary use/ NHSE perspective. | TM | CLOSED | 20.11.2024 Closed 15.11.2023 NEW. | shared
72 | 15.11.2023 | Mirror published information about 25/26 ERF reimbursement | JS/JE | CLOSED | 23.07.2025 done
71 | 21.05.2025 | Produce an article to explain the different data flows out of SUS+ and how they can be updated | JS | CLOSED | 24.09.2025 document created 20.08.2025 No update